## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | SINGADDA AND ADJOINING MOUJAS PWSS | SM/13722 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1004/MURD/18 | 17/04/2023 | 17/04/2023 | Resource Division | 24.48 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Berhampore Mechanical | SINGADDA AND ADJOINING MOUJAS PWSS | SM/13722 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SINGADDA ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000067/2023-2024 | 1897/MEDB | 16/06/2023 | 01/08/2025 | ABHISEK ENGINEERING CONCERN | 22.61 | 0 | 0 | 30
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | SINGADDA AND ADJOINING MOUJAS PWSS | SM/13722 | New | NEW SERVICE CONNECTION PH 2 SINGADDA PWSS ID 304256291 |  |  | BILL/01450/2023-2024 | 343/WBSEDCL-JJM | 12/02/2024 | 12/02/2024 | WBSEDCL | 4.78 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | SINGADDA AND ADJOINING MOUJAS PWSS | SM/13722 | New | NEW SERVICE CONNECTION PH 1 SINGADDA PWSS ID 30425678 |  |  | BILL/01449/2023-2024 | 342/WBSEDCL-JJM | 12/02/2024 | 12/02/2024 | WBSEDCL | 5.13 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Murshidabad Division | SINGADDA AND ADJOINING MOUJAS PWSS | SM/13722 | New | Formal work order for the work of SINGADDA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte.( Scheme ID -PH222362264S000) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000712/2022-2023 | 91/MURD | 11/01/2023 | 01/06/2025 | PASCON | 565.86 | 0 | 0 | 39
Total | [13 empty] | 622.87 | 0 | 0