## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | ANDULIA AND ADJOININNG MOUJAS PWSS | SM/13723 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1004/MURD/12 | 17/04/2023 | 17/04/2023 | Resource Division | 24.19 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Berhampore Mechanical | ANDULIA AND ADJOININNG MOUJAS PWSS | SM/13723 | New | New service connection charge for Andulia, P/H No.-I. |  |  | BILL/00539/2023-2024 | 111/WBSEDCL-JJM | 29/08/2023 | 29/08/2023 | WBSEDCL | 5.47 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Berhampore Mechanical | ANDULIA AND ADJOININNG MOUJAS PWSS | SM/13723 | New | New service connection charge for Andulia, P/H No.-II. |  |  | BILL/00538/2023-2024 | 110/WBSEDCL-JJM | 29/08/2023 | 29/08/2023 | WBSEDCL | 8.54 | 0 | 0 | 0
4 | MURSHIDABAD | Kandi | Berhampore Mechanical | ANDULIA AND ADJOININNG MOUJAS PWSS | SM/13723 | New | Electric Service Connection at ANDULIA PWSS I, Application NO.3004400021, ID 304117200 |  |  | BILL/01083/2023-2024 | 197/WBSEDCL-JJM | 19/12/2023 | 19/12/2023 | WBSEDCL | 5.47 | 0 | 0 | 0
5 | MURSHIDABAD | Kandi | Berhampore Mechanical | ANDULIA AND ADJOININNG MOUJAS PWSS | SM/13723 | New | SERVICE CONNECTION CHARGES AT ANDULIA PH2 ID304117291 |  |  | BILL/01112/2023-2024 | 208/WBSEDCL-JJM | 02/01/2024 | 02/01/2024 | WBSEDCL | 8.54 | 0 | 0 | 0
6 | MURSHIDABAD | Kandi | Murshidabad Division | ANDULIA AND ADJOININNG MOUJAS PWSS | SM/13723 | New | RESTORATION OF DAMAGED ROAD DUE TO LAYING OF PHE PIPELINE OF MAHADIA-DURGAPUR ROAD FROM 0.30 KM TO 2.10 KM UNDER MSD HIGHWAY DIVISION.-II DURING THE YEAR OF 2024-25 |  |  | BILL/01073/2024-2025 | 393-MSD/2024-25 | 19/09/2024 | 19/09/2024 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 13.77 | 0 | 0 | 0
7 | MURSHIDABAD | Kandi | Berhampore Mechanical | ANDULIA AND ADJOININNG MOUJAS PWSS | SM/13723 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under ANDULIA ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000080/2023-2024 | 1884/MEDB | 16/06/2023 | 16/09/2023 | HARA PROSAD DAS | 25.86 | 0 | 0 | 30
Total | [13 empty] | 91.84 | 0 | 0