## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | JUGASWARA AND ADJOINING MOUJAS PWSS | SM/13724 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1210/MURD/37 | 02/05/2023 | 02/05/2023 | Resource Division | 1.42 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Murshidabad Division | JUGASWARA AND ADJOINING MOUJAS PWSS | SM/13724 | New | Material Requisition To Resource Division |  |  | RTOR000346/2023-2024 | 112/MURD/03 | 11/01/2024 | 11/01/2024 | Resource Division | 4.88 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | JUGASWARA AND ADJOINING MOUJAS PWSS | SM/13724 | New | NEW SERVICE CONNECTION AT PWSS PH 2 JUGASWARA ID 304240283 |  |  | BILL/01419/2023-2024 | 312/WBSEDCL-JJM | 05/02/2024 | 05/02/2024 | WBSEDCL | 9.89 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | JUGASWARA AND ADJOINING MOUJAS PWSS | SM/13724 | New | NEW SERVICE CONNECTION AT PWSS PH1 JUGASWARA ID 304240312 |  |  | BILL/01418/2023-2024 | 311/WBSEDCL-JJM | 05/02/2024 | 05/02/2024 | WBSEDCL | 4.88 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Murshidabad Division | JUGASWARA AND ADJOINING MOUJAS PWSS | SM/13724 | New | Formal Work Order ForConstruction of 100 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of JUGASWARA PWSS in Burwan Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362271S000) [(i)Amount for LDS , R.Main & FHTC: Rs.1,38,33,206.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs. 1,13,02,060.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER_BURWAN BLOCK | ORD/000757/2022-2023 | 416/MURD | 15/02/2023 | 14/02/2025 | SHYAMAL KUMAR SAHA | 251.3 | 0 | 0 | 90
6 | MURSHIDABAD | Burwan | Berhampore Mechanical | JUGASWARA AND ADJOINING MOUJAS PWSS | SM/13724 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of Jugaswara ground water based water supply scheme under Block- Burwan, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000098/2023-2024 | 1889/MEDB | 16/06/2023 | 16/09/2023 | ASSOCIATED ELECTRICAL CO. | 21.23 | 0 | 0 | 20
7 | MURSHIDABAD | Burwan | Murshidabad Division | JUGASWARA AND ADJOINING MOUJAS PWSS | SM/13724 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JUGASWARA PWSS at Head Work Site & 2nd Tube Well Site in Burwan Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER_BURWAN BLOCK | ORD/000770/2022-2023 | 485/MURD | 20/02/2023 | 06/04/2023 | NADIA TUBEWELLS | 16.81 | 0 | 0 | 100
Total | [13 empty] | 310.42 | 0 | 0