## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | MAHISAR AND ADJOINING MOUJAS PWSS | SM/13725 | New | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1043/MURD/13 | 17/04/2023 | 17/04/2023 | Resource Division | 26.09 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Berhampore Mechanical | MAHISAR AND ADJOINING MOUJAS PWSS | SM/13725 | New | Electric Service Connection at MAHISAR PWSS PH I, Application NO.3004403589, ID 304119890 |  |  | BILL/01084/2023-2024 | 195/WBSEDCL-JJM | 19/12/2023 | 19/12/2023 | WBSEDCL | 10.21 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Berhampore Mechanical | MAHISAR AND ADJOINING MOUJAS PWSS | SM/13725 | New | Electric Service Connection at MAHISAR PWSS PH II, Application NO.3004403661, ID 304119931 |  |  | BILL/01085/2023-2024 | 196/WBSEDCL-JJM | 19/12/2023 | 19/12/2023 | WBSEDCL | 10.29 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Murshidabad Division | MAHISAR AND ADJOINING MOUJAS PWSS | SM/13725 | New | Formal work order for the work of MAHISAR & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362278S000 | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000678/2022-2023 | 37/MURD | 04/01/2023 | 01/12/2025 | NAYLA CONSTRUCTION | 611.61 | 123.44 | 20.18 | 50
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | MAHISAR AND ADJOINING MOUJAS PWSS | SM/13725 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under MAHISAR ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000153/2023-2024 | 2083/MEDB | 19/06/2023 | 31/12/2025 | JOGMAYA ENGINEERING | 23.47 | 17.97 | 76.54 | 50
Total | [13 empty] | 681.66 | 141.41 | 20.74