## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | PARULIA AND ADJOINING MOUJAS PWSS | SM/13726 | New | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1004/MURD/15 | 17/04/2023 |  | Resource Division | 46.68 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Berhampore Mechanical | PARULIA AND ADJOINING MOUJAS PWSS | SM/13726 | New | NEW SERVICE CONNECTION AT PH1 PARULIA PWSS ID 304187861 |  |  | BILL/01130/2023-2024 | 222/WBSEDCL-JJM | 05/01/2024 |  | WBSEDCL | 11.66 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Berhampore Mechanical | PARULIA AND ADJOINING MOUJAS PWSS | SM/13726 | New | NEW SERVICE CONNECTION AT PH1 PARULIA PWSS ID 304187861 |  |  | BILL/01130/2023-2024 | 222/WBSEDCL-JJM | 05/01/2024 |  | WBSEDCL | 11.66 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Berhampore Mechanical | PARULIA AND ADJOINING MOUJAS PWSS | SM/13726 | New | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under PARULIA ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001428/2023-2024 | 4343/MEDB | 29/12/2023 | 28/03/2024 | M/S S. S. ENTERPRISE (DOMKAL) | 23.45 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | PARULIA AND ADJOINING MOUJAS PWSS | SM/13726 | New | NEW SERVICE CONNECTION AT PARULIA PH II, ID304233543 |  |  | BILL/01215/2023-2024 | 295/WBSEDCL-JJM | 01/02/2024 |  | WBSEDCL | 4.74 | 0 | 0 | 0
6 | MURSHIDABAD | Khargram | Berhampore Mechanical | PARULIA AND ADJOINING MOUJAS PWSS | SM/13726 | New | NEW SERVICE CONNECTION AT PARULIA PH II, ID304233543 |  |  | BILL/01215/2023-2024 | 295/WBSEDCL-JJM | 01/02/2024 |  | WBSEDCL | 4.74 | 0 | 0 | 0
7 | MURSHIDABAD | Khargram | Murshidabad Division | PARULIA AND ADJOINING MOUJAS PWSS | SM/13726 | New | Allied work of PARULIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000741/2023-2024 | 66/MURD | 08/01/2024 | 08/03/2024 | M/S.TAPAS KUMAR CHAKRABORTY | 53.37 | 0 | 0 | 0
8 | MURSHIDABAD | Khargram | Murshidabad Division | PARULIA AND ADJOINING MOUJAS PWSS | SM/13726 | New | Formal work order for the work of PARULIA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362284S000) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000693/2022-2023 | 165/MURD | 17/01/2023 | 17/01/2024 | M/S.TAPAS KUMAR CHAKRABORTY | 677.2 | 283.31 | 41.84 | 41
Total | [13 empty] | 833.5 | 283.31 | 33.99