## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | JASOHARI PIPE WATER SUPPLY SCHEME. | SM/13728 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JASOHARI PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000652/2022-2023 | 3400/MURD | 22/12/2022 | 05/02/2023 | M/S B.R. SUPPLIERS | 16.8 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Murshidabad Division | JASOHARI PIPE WATER SUPPLY SCHEME. | SM/13728 | New | Formal Work Order For Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of JASOHARI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362341S000) [ (i)Amount for LDS , R. Main & FHTC: Rs. 1,91,63,541.00 & (ii) Amount for OHR,Boundwary Wall & Pump House : Rs. 1,56,48,969.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000765/2022-2023 | 481/MURD | 20/02/2023 | 20/02/2024 | M/S. NANDY ENTERPRISE | 347.6 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Berhampore Mechanical | JASOHARI PIPE WATER SUPPLY SCHEME. | SM/13728 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under JASOHARI ground water based water supply scheme under Block_ KANDI Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000150/2023-2024 | 2081/MEDB | 19/06/2023 | 19/09/2023 | SARKAR CONSTRUCTION | 23.39 | 19.23 | 82.23 | 60
4 | MURSHIDABAD | Kandi | Murshidabad Division | JASOHARI PIPE WATER SUPPLY SCHEME. | SM/13728 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1004/MURD/8 | 11/04/2023 | 11/04/2023 | Resource Division | 24.37 | 0 | 0 | 0
Total | [13 empty] | 412.17 | 19.23 | 4.67