## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | BRAHMANDIHI AND ADJOINING MOUJAS PWSS | SM/13729 | New | Formal work order for the work of BRAHMANDIHI & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division , PHE. Dte.( Scheme ID -PH222362353S000) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000677/2022-2023 | 36/MURD | 04/01/2023 | 01/10/2025 | TRANS ORGANICS (INDIA) PVT. LTD. | 526.07 | 99 | 18.82 | 20
2 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | BRAHMANDIHI AND ADJOINING MOUJAS PWSS | SM/13729 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BRAHMANDIHI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000083/2023-2024 | 1885/MEDB | 16/06/2023 | 16/09/2023 | M/S S. R. ENTERPRISE | 23.47 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | BRAHMANDIHI AND ADJOINING MOUJAS PWSS | SM/13729 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1043/MURD/14 | 17/04/2023 | 17/04/2023 | Resource Division | 34.54 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | BRAHMANDIHI AND ADJOINING MOUJAS PWSS | SM/13729 | New | Quotation for Bamundi PH No-1 |  |  | BILL/01433/2023-2024 | 329/WBSEDCL-JJM | 06/02/2024 | 06/02/2024 | WBSEDCL | 4.36 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | BRAHMANDIHI AND ADJOINING MOUJAS PWSS | SM/13729 | New | NEW CONNECTION AT BRAHMANDIHI PH-II |  |  | BILL/01485/2024-2025 | 455/WBSEDCL-JJM | 27/03/2025 | 27/03/2025 | WBSEDCL | 5.26 | 0 | 0 | 0
Total | [13 empty] | 593.7 | 99 | 16.67