## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SIJGRAM AND ADJOINING MOUJAS PWSS | SM/13730 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1210/MURD/34 | 02/05/2023 | 02/05/2023 | Resource Division | 42.92 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SIJGRAM AND ADJOINING MOUJAS PWSS | SM/13730 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SIJGRAM PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000660/2022-2023 | 3405/MURD | 22/12/2022 | 05/02/2023 | M/S D. PALIT & CO. | 16.81 | 0 | 0 | 100
3 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | SIJGRAM AND ADJOINING MOUJAS PWSS | SM/13730 | New | NEW SERVICE CONNECTION AT SIJGRAM PH 1 PWSS ID 304201248 |  |  | BILL/01131/2023-2024 | 221/WBSEDCL-JJM | 05/01/2024 | 05/01/2024 | WBSEDCL | 5.03 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | SIJGRAM AND ADJOINING MOUJAS PWSS | SM/13730 | New | Sijgram ph-2 Application No- 3004401470 |  |  | BILL/01180/2023-2024 | 242/WBSEDCL-JJM | 15/01/2024 | 15/01/2024 | WBSEDCL | 8.65 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | SIJGRAM AND ADJOINING MOUJAS PWSS | SM/13730 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SIJGRAM ground water based water supply scheme under Block_ Bharatpur-I, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000106/2023-2024 | 1893/MEDB | 16/06/2023 | 01/12/2025 | SUNIL RABIDAS | 22.58 | 0 | 0 | 5
6 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SIJGRAM AND ADJOINING MOUJAS PWSS | SM/13730 | New | Formal work order for Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of SIJGRAM PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362356S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,23,22,548.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,57,06,711.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000745/2022-2023 | 412/MURD | 15/02/2023 | 01/12/2025 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 280.01 | 0 | 0 | 11
7 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SIJGRAM AND ADJOINING MOUJAS PWSS | SM/13730 | New | Allied work of Construction of 2nos. Box Culvert, approach road at Sijgram PWSS at Bharatpur -I Block under Kandi Sub-Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000046/2024-2025 | 1893/MURD | 01/07/2024 | 28/02/2025 | RIM CONSTRUCTION | 44.07 | 0 | 0 | 10
8 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SIJGRAM AND ADJOINING MOUJAS PWSS | SM/13730 | New | Formal work order for Laying Distribution System (PART -A) of SIJGRAM PWSS of Bharatpur - I Block, Kandi Sub Division under Murshidabad District, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000697/2022-2023 | 132 / MURD | 16/01/2023 | 01/03/2025 | JIBENDRA NARAYAN SUKUL | 136.47 | 0 | 0 | 67
Total | [13 empty] | 556.54 | 0 | 0