## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under GUNANANDABATI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000089/2023-2024 | 1888/MEDB | 16/06/2023 | 16/09/2023 | ASHUTOSH DAS & CO. | 23.47 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1210/MURD/43 | 02/05/2023 | 02/05/2023 | Resource Division | 20.97 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | New | Formal work order for Laying Distribution System (PART-A) of Gunanandabati PWSS at Bharatpur-I Block, Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362380S000) | ASSISTANT ENGINEER | JUNIOR ENGINEER 8,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000698/2022-2023 | 131/MURD | 16/01/2023 | 13/12/2024 | HARAPRASAD DAS | 132.64 | 0 | 0 | 85
4 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GUNANANDABATI PWSS at Head Work Site & 2nd Tube Well Site in Bharatpur-I Block under Kandi SubDivision, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 8,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000659/2022-2023 | 3404/MURD | 22/12/2022 | 05/02/2023 | M/S D. PALIT & CO. | 16.81 | 0 | 0 | 100
5 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | New | Formal work order for Construction of 250 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of GUNANANDABATI PWSS in Bharatpur-I Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362380S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,31,40,916.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,49,38,880.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 8,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000763/2022-2023 | 479/MURD | 20/02/2023 | 20/02/2024 | S.&P. ENTERPRISE | 280.74 | 0 | 0 | 0
6 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | New | Laying Distribution system, of Gunanadabati PWSS in Bharatpur-I Block of Kandi Sub-Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 8,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000183/2024-2025 | 3147/MURD | 03/12/2024 | 31/05/2025 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 21.46 | 0 | 0 | 80
Total | [13 empty] | 496.08 | 0 | 0