## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under GUNANANDABATI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000089/2023-2024 | 1888/MEDB | 16/06/2023 | 16/09/2023 | ASHUTOSH DAS & CO. | 23.47 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1210/MURD/43 | 02/05/2023 | 02/05/2023 | Resource Division | 20.97 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | New | Formal work order for Laying Distribution System (PART-A) of Gunanandabati PWSS at Bharatpur-I Block, Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362380S000) | ASSISTANT ENGINEER | JUNIOR ENGINEER 8,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000698/2022-2023 | 131/MURD | 16/01/2023 | 13/12/2024 | HARAPRASAD DAS | 132.64 | 120.71 | 91.01 | 85
4 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GUNANANDABATI PWSS at Head Work Site & 2nd Tube Well Site in Bharatpur-I Block under Kandi SubDivision, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 8,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000659/2022-2023 | 3404/MURD | 22/12/2022 | 05/02/2023 | M/S D. PALIT & CO. | 16.81 | 13.8 | 82.12 | 100
5 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | New | Laying Distribution system, of Gunanadabati PWSS in Bharatpur-I Block of Kandi Sub-Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 8,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000183/2024-2025 | 3147/MURD | 03/12/2024 | 31/05/2025 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 21.46 | 0 | 0 | 80
6 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS | SM/13731 | New | Construction of RCC Retaining Wall for Gunanandabati PWSS at Bharatpur-I Block under Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 8 | ORD/000825/2023-2024 | 767/MURD | 13/03/2024 | 09/07/2025 | M.R. ENTERPRISE (MD. HASANUZZAMAN) | 20.69 | 19.34 | 93.49 | 100
Total | [13 empty] | 236.03 | 153.85 | 65.18