## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS | SM/13732 | New | Material Requisition To Resource Division |  |  | RTOR000316/2023-2024 | 1936/MURD/3 | 18/07/2023 | 18/07/2023 | Resource Division | 25.21 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Berhampore Mechanical | BUNDI AND ADJOINING MOUJAS PWSS | SM/13732 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Bundi ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000085/2023-2024 | 1886/MEDB | 16/06/2023 | 16/09/2023 | M/S SAJAHAN CHOWDHURY | 22.54 | 14.31 | 63.52 | 5
3 | MURSHIDABAD | Kandi | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS | SM/13732 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 0 | 0 | 80
4 | MURSHIDABAD | Kandi | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS | SM/13732 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BUNDAI PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000653/2022-2023 | 3403/MURD | 22/12/2022 | 05/02/2023 | M/S SUBHAJIT BISWAS | 16.8 | 15.2 | 90.45 | 75
5 | MURSHIDABAD | Kandi | Berhampore Mechanical | BUNDI AND ADJOINING MOUJAS PWSS | SM/13732 | New | SHIFTING OF 11KV AT BUNDAI |  |  | BILL/01582/2023-2024 | 449/WBSEDCL-JJM | 15/03/2024 | 15/03/2024 | WBSEDCL | 0.98 | 0 | 0 | 0
6 | MURSHIDABAD | Kandi | Berhampore Mechanical | BUNDI AND ADJOINING MOUJAS PWSS | SM/13732 | New | BUNDI PH 1 ID 304259360 |  |  | BILL/01476/2023-2024 | 365/WBSEDCL-JJM | 20/02/2024 | 20/02/2024 | WBSEDCL | 3.48 | 0 | 0 | 0
7 | MURSHIDABAD | Kandi | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS | SM/13732 | New | Formal Work Order for construction of 250 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of BUNDAI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362420S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,40,40,803.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,49,29,128.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000750/2022-2023 | 413/MURD | 15/02/2023 | 01/08/2025 | M/S TRADE ASSOCIATE | 289.47 | 39.33 | 13.59 | 20
8 | MURSHIDABAD | Kandi | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS | SM/13732 | New | Formal work order for the work of Laying Distribution System (PART-A) for Augmentation of BUNDAI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362420S000) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000973/2022-2023 | 130./MURD | 16/01/2023 | 01/07/2025 | PRASANTA SANA | 108.95 | 65.02 | 59.67 | 60
9 | MURSHIDABAD | Kandi | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS | SM/13732 | New | Balance work of road restoration damaged during laying of pipeline and laying of distribution pipe line of Bundai Piped Water Supply Scheme, Kandi Block, Kandi Sub-Division under Murshidabad Division, P.H.E dte. | ASSISTANT ENGINEER | Junior Engineer, Estimating Section | ORD/000845/2023-2024 | 827/MURD | 15/03/2024 | 30/03/2024 | PRASANTA SANA | 20.72 | 6.51 | 31.4 | 50
10 | MURSHIDABAD | Kandi | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS | SM/13732 | New | Balance work for repair of road, construction of approach road & land development of Hizole-I & II & Bundai Water Supply Scheme of Kandi Block under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000006/2025-2026 | 835/MURD | 11/04/2025 | 01/12/2025 | M/S JATIN | 69.3 | 0 | 0 | 5
Total | [13 empty] | 654.94 | 140.36 | 21.43