## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13824 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER |  | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 04/04/2022 | MERCHANDISE-INDIA | 105.32 | 12.3 | 11.68 | 1
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13824 | Augmentation | Formal work order for the Work of Augmentation of JITPUR ZONE-I & its adjoining mouzas Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000702/2022-2023 | 124/MURD | 16/01/2023 | 15/07/2023 | M/S. S. DAS AND ENTERPRISE | 488.01 | 184.14 | 37.73 | 15
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13824 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under JITPUR ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000053/2023-2024 | 3760/MEDB | 03/11/2023 | 03/02/2024 | JAGANNATH ENTERPRISE | 23.28 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13824 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 1210/MURD/10 | 02/05/2023 | 02/05/2023 | Resource Division | 2.76 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13824 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 2.62 | 2.69 | 80
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13824 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JITPUR (ZONE I) Water Supply Scheme at Head Work Site, 2nd Site site at DOMKAL Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000106/2023-2024 | 1748/MURD | 06/07/2023 | 27/07/2023 | MAMATA USHA ENTERPRISE | 23.58 | 20.18 | 85.57 | 100
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13824 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000391/2023-2024 | 526/MURD/01 | 19/02/2024 | 19/02/2024 | Resource Division | 9.83 | 0 | 0 | 0
Total | [13 empty] | 750.26 | 219.24 | 29.22