## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13825 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 1180/MURD/20 | 30/04/2023 | 30/04/2023 | Resource Division | 30.1 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13825 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , ZONE-II under JITPUR ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000054/2023-2024 | 03/MEDB | 02/01/2024 | 02/04/2024 | M/S K.P. PRAMANIK | 15.77 | 13.84 | 87.72 | 20
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13825 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II,III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JITPUR (ZONE II) Water Supply Scheme at Head Work Site, 2nd & 3rd Site site at DOMKAL Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000105/2023-2024 | 1747/MURD | 06/07/2023 | 27/07/2023 | MAMATA USHA ENTERPRISE | 35.37 | 31.12 | 87.98 | 100
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13825 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000392/2023-2024 | 526/MURD/02 | 19/02/2024 | 19/02/2024 | Resource Division | 6.83 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13825 | Augmentation | Jitpur Zone-2 PH-1 Application No- 3004547411 |  |  | BILL/01228/2023-2024 | 279/WBSEDCL-JJM | 24/01/2024 | 24/01/2024 | WBSEDCL | 10.38 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13825 | Augmentation | Jitpur Zone-2 PH-2 Application No-3004547163 |  |  | BILL/01226/2023-2024 | 278/WBSEDCL-JJM | 24/01/2024 | 24/01/2024 | WBSEDCL | 4.89 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13825 | Augmentation | NEW CONNECTION AT JITPUR Z-II PH-III |  |  | BILL/01102/2024-2025 |  | 13/11/2024 | 13/11/2024 | WBSEDCL | 6.3 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. | SM/13825 | Augmentation | Formal work order for Augmentation of JITPUR (Zone-II) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000796/2022-2023 | 603/MURD | 02/03/2023 | 01/01/2026 | M/S.TAPAS KUMAR CHAKRABORTY | 752.45 | 520.72 | 69.2 | 40
Total | [13 empty] | 862.1 | 565.68 | 65.62