## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | JAJAN AND ADJOINING MOUJAS PWSS | SM/13925 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 1075/MURD/8 | 19/04/2023 | 19/04/2023 | Resource Division | 22.01 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | JAJAN AND ADJOINING MOUJAS PWSS | SM/13925 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under JAJAN ground water based water supply scheme under Block_ BHARATPUR-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000051/2023-2024 | 1895/MEDB | 16/06/2023 | 16/09/2023 | HANNAN BUILDERS PVT LTD | 22.18 | 0 | 0 | 10
3 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | JAJAN AND ADJOINING MOUJAS PWSS | SM/13925 | New | New connection jajan ph-I |  |  | BILL/00241/2024-2025 | 109/WBSEDCL-JJM | 05/06/2024 | 05/06/2024 | WBSEDCL | 4.06 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | JAJAN AND ADJOINING MOUJAS PWSS | SM/13925 | New | JAJAN & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BHARATPUR-I of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000838/2022-2023 | 758/MURD | 16/03/2023 | 01/05/2025 | GOURANGA MONDAL | 343.34 | 0 | 0 | 10
5 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | JAJAN AND ADJOINING MOUJAS PWSS | SM/13925 | New | Allied work for Laying Distribution System, Construction of Boundary Wall, Approach Road & Land Development of Jajan PWSS in Bhratpur-I Block , KANDI Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000835/2023-2024 | 768/MURD | 13/03/2024 | 14/03/2025 | GOURANGA MONDAL | 59.79 | 0 | 0 | 10
Total | [13 empty] | 451.38 | 0 | 0