## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 1043/MURD/2 | 17/04/2023 | 17/04/2023 | Resource Division | 8.9 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000307/2023-2024 | 1295/MURD/02 | 11/05/2023 | 11/05/2023 | Resource Division | 8.9 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Laying Distribution System PART-B,FHTC for Augmentation of GOBARHATI PWSS in KANDI Block , under Murshidabad Division ,PHE.Dte.Part-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000017/2023-2024 | 991/MURD | 11/04/2023 | 09/08/2023 | S.K. ENTERPRISE (SANDIP GHOSH) | 175.23 | 172.6 | 98.49 | 35
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Construction of surface drain of length 50 m at the Head work site of Gobarhati PWSS and Southern side of Kandi Stack Yard under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000166/2023-2024 | 1971/MURD | 20/07/2023 | 19/08/2023 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 3.88 | 3.85 | 99.4 | 100
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Supplying fitting and fixing of R.B. T Concertina fencing on wall top of Gobarhati PWSS and Kandi Stack Yard under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000167/2023-2024 | 1972/MURD | 20/07/2023 | 19/08/2023 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 5.14 | 4.91 | 95.56 | 80
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Construction of surface drain of length 40.35 m at the Head work site of Gobarhati PWSS and eastern side of Kandi Stack Yard under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000747/2023-2024 | 106/MURD | 10/01/2024 | 09/02/2024 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 3.06 | 2.92 | 95.57 | 100
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Demolition of damaged R.C.C. Elevated Reservoir (Capacity 2,72,400 Ltr) at Gokarna /Gobarhati Water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000737/2023-2024 | 61/MURD | 08/01/2024 | 07/02/2024 | MD SAJAHAN ALI | 5.47 | 5.47 | 100 | 100
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Construction of 350 Cum OHR, Boundwary Wall, Rising Main Connection, Laying Distribution System PART-A,FHTC for Augmentation of GOBARHATI PWSS in KANDI Block , under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000029/2023-2024 | 1087/MURD | 20/04/2023 | 19/04/2025 | MOTI RAHAMAN | 301.83 | 128.16 | 42.46 | 25
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Deputy Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For (05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05(Five) Months i.e. from 13/02/2025 to 12/07/2025].for the month of February 2025 to July2025 [Vehicle No.WB58AR5026] | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 8 | ORD/000475/2024-2025 | 390/MURD | 13/02/2025 | 13/07/2025 | MD MUKLESUR RAHAMAN | 0.87 | 1.9 | 218.87 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Executive Engineer, Murshidabad Division, P.H.E. Dte. For (06) Six Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order) [Period for 06 (Six) Months].for the month of April 2025 to October 2025 [Vehicle No.WB93B0287] (i.e. from 05/04/2025 to 04/10/2025) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 5,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000085/2025-2026 | 784/MURD | 03/04/2025 | 03/10/2025 | M/S. S. DAS AND ENTERPRISE | 0.75 | 0 | 0 | 25
11 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (GABARHATI PWSS Scheme, Block - KANDI) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/002140/2021-2022 | 3257/MURD | 05/10/2021 | 04/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 6.51 | 4.43 | 67.93 | 1
12 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well , 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gobarhati & Hizole Water Supply Scheme at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000034/2023-2024 | 1109/MURD | 24/04/2023 | 16/04/2025 | INDRAJIT MAZUMDAR | 10.68 | 0 | 0 | 100
13 | MURSHIDABAD |  | Central Drilling | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
14 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Deputy Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For(05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05(Five) Months i.e. from 13/07/2025 to 12/12/2025].for the month of July 2025 to December 2025 [Vehicle No.WB58AR5026] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2,JUNIOR ENGINEER 8 | ORD/000092/2025-2026 | 1575/MURD | 11/07/2025 | 11/12/2025 | MD MUKLESUR RAHAMAN | 0.75 | 0 | 0 | 20
15 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover any where with in any trouble on daily wage basis for official used under the control of the Executive Engineer, Murshidabad Division, P.H.E. Dte. For (06) Six Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order) [Period for 06 (Six) Months].for the month of September 2025 to March 2026 [Vehicle No.WB93B 0287] (i.e. from 05/09/2025 to 05/03/2026) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION,Junior Engineer 3,JUNIOR ENGINEER 5,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000186/2025-2026 | 1948/MURD | 01/09/2025 | 02/03/2026 | M/S. S. DAS AND ENTERPRISE | 0.89 | 0 | 0 | 0
16 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Deputy Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For(05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05(Five) Months i.e. from 13/12/2025 to 14/05/2026].for the month of DECEMBER 2025 to MAY 2026 [Vehicle No.WB58AR5026] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2,JUNIOR ENGINEER 8 | ORD/000251/2025-2026 | 2560/MURD | 10/12/2025 | 10/05/2026 | MD MUKLESUR RAHAMAN | 0.75 | 0 | 0 | 0
Total | [13 empty] | 21873.37 | 324.23 | 1.48