## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (GABARHATI PWSS Scheme, Block - KANDI) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/002140/2021-2022 | 3257/MURD | 05/10/2021 | 04/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 6.51 | 4.43 | 67.93 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 1043/MURD/2 | 17/04/2023 |  | Resource Division | 8.9 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000307/2023-2024 | 1295/MURD/02 | 11/05/2023 |  | Resource Division | 8.9 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Demolition of damaged R.C.C. Elevated Reservoir (Capacity 2,72,400 Ltr) at Gokarna /Gobarhati Water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000737/2023-2024 | 61/MURD | 08/01/2024 | 07/02/2024 | MD SAJAHAN ALI | 5.47 | 2.73 | 50 | 100
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Construction of surface drain of length 40.35 m at the Head work site of Gobarhati PWSS and eastern side of Kandi Stack Yard under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000747/2023-2024 | 106/MURD | 10/01/2024 | 09/02/2024 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 3.06 | 1.46 | 47.78 | 100
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Supplying fitting and fixing of R.B. T Concertina fencing on wall top of Gobarhati PWSS and Kandi Stack Yard under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000167/2023-2024 | 1972/MURD | 20/07/2023 | 19/08/2023 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 5.14 | 2.46 | 47.78 | 80
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gobarhati & adjoining mouzas Water Supply Scheme at 3rd work site at K a n d i Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000034/2023-2024 | 1109/MURD | 24/04/2023 | 14/05/2023 | INDRAJIT MAZUMDAR | 10.68 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Construction of 350 Cum OHR, Boundwary Wall, Rising Main Connection, Laying Distribution System PART-A,FHTC for Augmentation of GOBARHATI PWSS in KANDI Block , under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000029/2023-2024 | 1087/MURD | 20/04/2023 | 19/04/2024 | MOTI RAHAMAN | 301.83 | 98.39 | 32.6 | 25
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Laying Distribution System PART-B,FHTC for Augmentation of GOBARHATI PWSS in KANDI Block , under Murshidabad Division ,PHE.Dte.Part-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000017/2023-2024 | 991/MURD | 11/04/2023 | 09/08/2023 | S.K. ENTERPRISE (SANDIP GHOSH) | 175.23 | 93.78 | 53.52 | 35
10 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Construction of surface drain of length 50 m at the Head work site of Gobarhati PWSS and Southern side of Kandi Stack Yard under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000166/2023-2024 | 1971/MURD | 20/07/2023 | 19/08/2023 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 3.88 | 3.85 | 99.4 | 100
11 | MURSHIDABAD |  | Central Drilling | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. | SM/13926 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21869.37 | 207.1 | 0.95