## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000208/2023-2024 | 1210/MURD/24 | 02/05/2023 | 02/05/2023 | Resource Division | 4.36 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001641/2021-2022 | 480/MURD | 22/02/2022 | 23/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , ZONE-I under BACHHRA ground water based water supply scheme under Block_ BELDANGA-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001473/2023-2024 | 758/MEDB | 20/02/2024 | 20/05/2024 | KARTICK BAL | 36.55 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 0 | 0 | 80
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 1811/MURD/11 | 20/06/2024 | 20/06/2024 | Resource Division | 6.03 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | NEW CONNECTION AT BACHRA Z-I PH-I |  |  | BILL/00173/2024-2025 | 18/WBSEDCL-JJM | 16/04/2024 | 16/04/2024 | WBSEDCL | 3.76 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Construction of 100 Cum OHR, Laying of Distribution System (part_A), Rising Main , Special repair and renovation of existing 1 (One) Nos PumpHouse and Allied Works, repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity for Augmentation work of BACHHRA ZONE-I PWSS in BELDANGA-II Block under Murshidabad Division , PHE.Dte.(part_A) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000138/2023-2024 | 1820/MURD | 12/07/2023 | 01/07/2025 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 330.74 | 0 | 0 | 5
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 19/12/2024 | SUJIT MONDAL | 7.27 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For(05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05 (Five) Months].for the month of December 2024 to April 2025 [Vehicle No.WB25M1561] (i.e. from 01/12/2024 to 30/04/2025) | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE | ORD/000199/2024-2025 | 3127/MURD | 30/11/2024 | 30/04/2025 | M/S B K ENTERPRISE | 0.87 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for BACHHRA ZONE-II Ground Based Water Supply Scheme in Beldanga -II Block underMurshidabad Division , PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000031/2025-2026 | 1194/MURD | 23/05/2025 | 22/07/2025 | M/S UNIVERSAL TRADING | 19.62 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 01/08/2025 | M/S. BIMALENDU BOSE | 46.93 | 0 | 0 | 75
12 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Providing FHTC Connection to 573 nos household , Laying of Distribution System (Part_B), Repairing & Vertical Extention of Boundary Wall for Augmentation work of BACHHARA ZONE-I PWSS in Beldanga-II Block under Murshidabad Division , PHE.Dte. (part_B) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000890/2022-2023 | 913/MURD | 30/03/2023 | 21/02/2025 | AYUSH ENTERPRISE | 103.18 | 0 | 0 | 80
13 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BACHHRA ZONE ¿ I Water Supply Scheme at Head Work Site, 2nd Site site at Beldanga-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000551/2023-2024 | 3193/MURD | 12/10/2023 | 05/02/2025 | NADIA TUBEWELLS | 23.56 | 0 | 0 | 100
14 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. | SM/13928 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 28/07/2024 | IMAGIN | 95.53 | 0 | 0 | 100
Total | [13 empty] | 823.21 | 0 | 0