## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/13931 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia Replacement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SANTOSHPUR PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000658/2022-2023 | 3415/MURD | 22/12/2022 | 05/02/2023 | HARUN ALL RASHID & BROTHERS | 16.64 | 13.69 | 82.31 | 80
2 | MURSHIDABAD | Kandi | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/13931 | New | Formal work order for construction of 250 Cum OHR , Laying Distribution System (PART-A), Rising Main, FHTC, for Uncovered SANTOSHPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. [ (i) Amount for LDS , R.Main & FHTC: Rs.2,44,40,742.00 & (ii) Amount for OHR: Rs.1,03,92,477.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000764/2022-2023 | 480/MURD | 20/02/2023 | 16/02/2026 | S.&P. ENTERPRISE | 348.26 | 93.02 | 26.71 | 15
3 | MURSHIDABAD | Kandi | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/13931 | New | Formal work order for Laying Distribution System (PART-B), Construction of Boundary Wall & Pump house for Uncovered SANTOSHPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. [ (i) Amount for Laying Distribution System: Rs.1,54,12,147.00 & (ii) Amount for Boundary Wall & Pump House: Rs. 41,19,886.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000727/2022-2023 | 176/MURD | 18/01/2023 | 01/11/2025 | MOTI RAHAMAN | 195.28 | 0 | 0 | 35
4 | MURSHIDABAD | Kandi | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/13931 | New | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1210/MURD/32 | 02/05/2023 | 02/05/2023 | Resource Division | 23.42 | 0 | 0 | 0
5 | MURSHIDABAD | Kandi | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/13931 | New | Material Requisition To Resource Division |  |  | RTOR000317/2023-2024 | 1936/MURD/5 | 19/07/2023 | 19/07/2023 | Resource Division | 23.42 | 0 | 0 | 0
6 | MURSHIDABAD | Kandi | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/13931 | New | Material Requisition To Resource Division |  |  | RTOR000344/2023-2024 | 112/MURD/01 | 11/01/2024 | 11/01/2024 | Resource Division | 13.66 | 0 | 0 | 0
7 | MURSHIDABAD | Kandi | Berhampore Mechanical | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/13931 | New | AT SANTOSHPUR PH 1 ID 304252904 |  |  | BILL/01470/2023-2024 | 364/WBSEDCL-JJM | 20/02/2024 | 20/02/2024 | WBSEDCL | 4.7 | 0 | 0 | 0
8 | MURSHIDABAD | Kandi | Berhampore Mechanical | SANTOSHPUR AND ADJOINING MOUJAS PWSS | SM/13931 | New | SANTOSHPUR PH 2 C ID 304252909 |  |  | BILL/01469/2023-2024 | 363/WBSEDCL-JJM | 20/02/2024 | 20/02/2024 | WBSEDCL | 3.33 | 0 | 0 | 0
Total | [13 empty] | 628.71 | 106.72 | 16.97