## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | PUNRAPARA AND ADJOINING MOUJAS PWSS | SM/13932 | New | Formal Work Order for Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, Boundwary Wall for PUNRAPARA PWSS in Khargram Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000844/2022-2023 | 756/MURD | 16/03/2023 | 01/02/2026 | JIT CONSTRUCTION | 194.6 | 85.37 | 43.87 | 25
2 | MURSHIDABAD | Khargram | Berhampore Mechanical | PUNRAPARA AND ADJOINING MOUJAS PWSS | SM/13932 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II,III ,IV & V under PUNRAPARA ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000084/2023-2024 | 1932/MEDB | 16/06/2023 | 16/09/2023 | MAHADEB ENTERPRISE | 55.86 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Murshidabad Division | PUNRAPARA AND ADJOINING MOUJAS PWSS | SM/13932 | New | Laying Distribution System (PART-B), FHTC for PUNRAPARA Water Supply Scheme in Khargram Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000675/2023-2024 | 3656/MURD | 29/11/2023 | 28/03/2024 | AJAY MONDAL | 270.3 | 81.52 | 30.16 | 30
4 | MURSHIDABAD | Khargram | Murshidabad Division | PUNRAPARA AND ADJOINING MOUJAS PWSS | SM/13932 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Punrapara & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000039/2023-2024 | 1099/MURD | 24/04/2023 | 24/05/2023 | NADIA TUBEWELLS | 21.35 | 18.97 | 88.83 | 100
5 | MURSHIDABAD | Khargram | Murshidabad Division | PUNRAPARA AND ADJOINING MOUJAS PWSS | SM/13932 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PUNRAPARA, Augmentation of Bahara & Pacchipara Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000269/2023-2024 | 2587/MURD | 21/08/2023 | 01/11/2024 | INDRAJIT MAZUMDAR | 18.43 | 0 | 0 | 60
6 | MURSHIDABAD | Khargram | Murshidabad Division | PUNRAPARA AND ADJOINING MOUJAS PWSS | SM/13932 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1210/MURD/33 | 02/05/2023 | 02/05/2023 | Resource Division | 16.9 | 0 | 0 | 0
7 | MURSHIDABAD | Khargram | Berhampore Mechanical | PUNRAPARA AND ADJOINING MOUJAS PWSS | SM/13932 | New | NEW CONNECTION AT PURAOARA PH 1 ID 304342318 |  |  | BILL/00357/2024-2025 | 108/WBSEDCL-JJM | 05/06/2024 | 05/06/2024 | WBSEDCL | 6.06 | 0 | 0 | 0
Total | [13 empty] | 583.49 | 185.86 | 31.85