## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | MUNIGRAM AND ADJOINING MOUJAS PWSS | SM/13935 | New | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 1067/MURD/7 | 18/04/2023 | 18/04/2023 | Resource Division | 1.38 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Berhampore Mechanical | MUNIGRAM AND ADJOINING MOUJAS PWSS | SM/13935 | New | Electric Service Connection at MUNIGRAM, Application NO.3004466957, ID 304171251 |  |  | BILL/01080/2023-2024 | 194/WBSEDCL-JJM | 19/12/2023 | 19/12/2023 | WBSEDCL | 5.16 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Berhampore Mechanical | MUNIGRAM AND ADJOINING MOUJAS PWSS | SM/13935 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MUNIGRAM ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000171/2023-2024 | 2017/MEDB | 19/06/2023 | 19/09/2023 | T. S. CONSTRUCTION | 22.22 | 0 | 0 | 60
4 | MURSHIDABAD | Kandi | Murshidabad Division | MUNIGRAM AND ADJOINING MOUJAS PWSS | SM/13935 | New | Sinking of 02 (Two) Nos. of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MUNIGARM AND ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at KANDI Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000270/2023-2024 | 2588/MURD | 21/08/2023 | 11/09/2023 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 0 | 80
5 | MURSHIDABAD | Kandi | Murshidabad Division | MUNIGRAM AND ADJOINING MOUJAS PWSS | SM/13935 | New | Material Requisition To Resource Division |  |  | RTOR000364/2023-2024 | MURD/439/13 | 08/02/2024 | 08/02/2024 | Resource Division | 6.34 | 0 | 0 | 0
6 | MURSHIDABAD | Kandi | Berhampore Mechanical | MUNIGRAM AND ADJOINING MOUJAS PWSS | SM/13935 | New | AT MUNIGRAM PH 2 ID 304252906 |  |  | BILL/01471/2023-2024 | 362/WBSEDCL-JJM | 20/02/2024 | 20/02/2024 | WBSEDCL | 4.88 | 0 | 0 | 0
7 | MURSHIDABAD | Kandi | Murshidabad Division | MUNIGRAM AND ADJOINING MOUJAS PWSS | SM/13935 | New | Formal work order for the work of MUNIGRAM & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall, IEP and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000715/2022-2023 | 106/MURD | 13/01/2023 | 01/08/2025 | PRANAB KUMAR GHOSH | 279.43 | 0 | 0 | 30
Total | [13 empty] | 337.85 | 0 | 0