## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13936 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1067/MURD/6 | 18/04/2023 |  | Resource Division | 24.66 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Berhampore Mechanical | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13936 | New | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MAHAMMADPUR ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000158/2023-2024 | 2016/MEDB | 19/06/2023 | 17/09/2023 | A.G. ENTERPRISE | 20.38 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Murshidabad Division | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13936 | New | Material Requisition To Resource Division |  |  | RTOR000336/2023-2024 | 79/MURD/03 | 09/01/2024 |  | Resource Division | 8.45 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Murshidabad Division | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13936 | New | Material Requisition To Resource Division |  |  | RTOR000350/2023-2024 | 112/MURD/07 | 11/01/2024 |  | Resource Division | 8.45 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13936 | New | new service connection at MAHAMMADPUR PH2 ID304222150 |  |  | BILL/01146/2023-2024 | 228/WBSEDCL-JJM | 09/01/2024 |  | WBSEDCL | 4.75 | 0 | 0 | 0
6 | MURSHIDABAD | Khargram | Berhampore Mechanical | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13936 | New | new service connection at MAHAMMADPUR PH2 ID304222150 |  |  | BILL/01146/2023-2024 | 228/WBSEDCL-JJM | 09/01/2024 |  | WBSEDCL | 4.75 | 0 | 0 | 0
7 | MURSHIDABAD | Khargram | Berhampore Mechanical | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13936 | New | NEW SERVICE CONNECTION AT MAHHAMMADPUR PH1 ID304222178 |  |  | BILL/01147/2023-2024 | 229/WBSEDCL-JJM | 09/01/2024 |  | WBSEDCL | 2.7 | 0 | 0 | 0
8 | MURSHIDABAD | Khargram | Berhampore Mechanical | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13936 | New | NEW SERVICE CONNECTION AT MAHHAMMADPUR PH1 ID304222178 |  |  | BILL/01147/2023-2024 | 229/WBSEDCL-JJM | 09/01/2024 |  | WBSEDCL | 2.7 | 0 | 0 | 0
9 | MURSHIDABAD | Khargram | Murshidabad Division | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13936 | New | Formal work order for the work of MAHAMMADPUR & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000710/2022-2023 | 143/MURD | 17/01/2023 | 17/01/2024 | SUJIT KUMAR SAHA | 315.18 | 74.97 | 23.79 | 70
Total | [13 empty] | 392.01 | 74.97 | 19.13