## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13992 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,ZONE-I under HAFANIA ground water based water supply scheme under Block_ Suti-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000126/2023-2024 | 1913/MEDB | 16/06/2023 | 16/09/2023 | CONCORD ENGINEERING | 33.22 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13992 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000265/2023-2024 | 1230/MURD/04 | 04/05/2023 | 04/05/2023 | Resource Division | 10.57 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13992 | Augmentation | HAFANIA PH-I Z-1 |  |  | BILL/01436/2023-2024 | 339/WBSEDCL-JJM | 07/02/2024 | 07/02/2024 | WBSEDCL | 3.64 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13992 | Augmentation | SHIFTING OF HT LINE AT HAFANIA Z-I |  |  | BILL/00431/2024-2025 | 146/WBSEDCL-JJM | 08/07/2024 | 08/07/2024 | WBSEDCL | 7.3 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13992 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 231/4 & 231/5) on railway land of mouza Hafania & Connecting with existing 160 mm dia uPVC distribution main line of Hafania ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000512/2021-2022 | 2480/MURD | 16/08/2021 | 15/10/2021 | M/S NIRAPADA BHATTACHARJEE | 28.91 | 0 | 0 | 100
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13992 | Augmentation | Formal Work Order for Augmentation of Ground Water Based HAFANIA (ZONE-I) PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000842/2022-2023 | 745/MURD | 16/03/2023 | 01/04/2025 | PAROMITA DEB | 416.04 | 0 | 0 | 40
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13992 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 230/6 & 230/7) at Hafania mouza & Connecting with existing 110 mm dia uPVC distribution main line of Hafania ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000513/2021-2022 | 2481/MURD | 16/08/2021 | 15/10/2021 | M/S NIRAPADA BHATTACHARJEE | 21.58 | 0 | 0 | 100
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13992 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 09/06/2022 | RADIANT | 73.97 | 0 | 0 | 100
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13992 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 28/07/2024 | IMAGIN | 95.53 | 0 | 0 | 100
Total | [13 empty] | 690.76 | 0 | 0