## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13994 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 225/3 & 225/4) at Khanpur mouza & Connecting with existing 110 mm dia UPVC distribution main line of Prosadpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000425/2021-2022 | 2482/MURD | 16/08/2021 | 15/10/2021 | DECON INDIA | 20.38 | 15.68 | 76.94 | 100
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13994 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 09/06/2022 | RADIANT | 73.97 | 3.86 | 5.22 | 100
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13994 | Augmentation | Providing FHTC to 1034 no household, Laying Distribution System, Vertical extension of Boundary wall and repairing Pump House and Overhauling of R.C.C. elevated reservoir 350 Cum capacity of staging height 20 mtr. (Shaft wall) for Augmentation work of Prosadpur (Zone-I) PWSS under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000886/2022-2023 | 905/MURD | 29/03/2023 | 01/09/2025 | M/S. S.S. ENTERPRISE( PROP: SANDIP SAHA) | 139.2 | 59.16 | 42.5 | 50
4 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13994 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under PRASADPUR ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000081/2023-2024 | 1931/MEDB | 16/06/2023 | 01/06/2026 | WEST BENGAL ENGINEERING CO. | 20.82 | 16.6 | 79.73 | 15
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13994 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000202/2023-2024 | 1210/MURD/28 | 02/05/2023 | 02/05/2023 | Resource Division | 1.51 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13994 | Augmentation | Laying of Distribution System (Part-A) & FHTC work at Khanpur, Bhairabpur, Khidirpur, Parulia village of PROSADPUR (ZONE-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000731/2023-2024 | 18/MURD | 03/01/2024 | 01/01/2026 | BISWAS ENTERPRISE (PROP. SAMIUL ISLAM)) | 84.13 | 26.59 | 31.61 | 41
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13994 | Augmentation | Allied work for Laying of UPVC pipeline, Construction of Culvert and Approach road for PROSADPUR (ZONE-I) Piped Water Supply Scheme in Suti-II Block of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,Junior Engineer 3 | ORD/000194/2024-2025 | 3213/MURD | 09/12/2024 | 08/01/2025 | M/S. S.S. ENTERPRISE( PROP: SANDIP SAHA) | 36.51 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13994 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for PRASADPUR ZONE-I Ground Based Water Supply Scheme in Suti-II Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000022/2025-2026 | 983/MURD | 02/05/2025 | 01/07/2025 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 19.61 | 0 | 0 | 0
Total | [13 empty] | 396.13 | 121.89 | 30.77