## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-A) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13995 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 1147/MURD/12 | 27/04/2023 | 27/04/2023 | Resource Division | 110.07 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-A) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13995 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000357/2023-2024 | 2713/MURD | 28/08/2023 | 17/09/2023 | RADIANT | 10.42 | 1.06 | 10.18 | 100
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-A) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13995 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2,Junior Engineer 3,JUNIOR ENGINEER 6 | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 01/01/2026 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 0 | 21
4 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-A) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/13995 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I and II ,ZONE-I under BAZEGAZIPUR ,PART-A ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000148/2023-2024 | 2080/MEDB | 19/06/2023 | 19/09/2023 | M/S S. S. ENTERPRISE (DOMKAL) | 25.46 | 19.42 | 76.28 | 8
Total | [13 empty] | 2710.36 | 20.48 | 0.76