## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/13996 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 7.92 | 9.72 | 100
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/13996 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 1278/MURD/19 | 10/05/2023 | 10/05/2023 | Resource Division | 34.76 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/13996 | Augmentation | Repairing of 550Cum OHR and FHTC for Augmentation of PUTIA (ZONE-I) ground water based piped water supply scheme within Raghunathganj-II Block under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000779/2022-2023 | 507/MURD | 22/02/2023 | 23/04/2023 | CLASSIC CONSTRUCTION (ANJAN CHATTERJEE) | 60.86 | 40.52 | 66.57 | 50
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/13996 | Augmentation | Renovation of Filter media of Existing AIRP (Capacity 135 Cum/hr.) of Putia (Zone-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000033/2024-2025 | 1892/MURD | 01/07/2024 | 30/08/2024 | M/S BAPPA ENTERPRISE | 47.01 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/13996 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PUTIA ZONE - I Water Supply Scheme at Head Work Site, 2nd Site, 3 r d , 4th site at RAGHUNATHGANJ - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000115/2023-2024 | 1759/MURD | 06/07/2023 | 27/07/2023 | MAMATA USHA ENTERPRISE | 35.37 | 25.42 | 71.87 | 80
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/13996 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000557/2024-2025 | 339/MEDB | 10/02/2025 | 30/12/2025 | M/S S. S. ENTERPRISE (DOMKAL) | 22.79 | 0 | 0 | 60
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/13996 | Augmentation | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month from 01/03/2025 to 31/08/2025] | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000513/2024-2025 | 66/JSD | 25/02/2025 | 25/08/2025 | ABHIJIT MAITRA | 0.88 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/13996 | Augmentation | Construction of approach road from pucca road to Head Work site of Putia Water Supply Scheme of Jangipur Sub-Division under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000656/2022-2023 | 3375/MURD | 20/12/2022 | 17/07/2025 | JAMIRUL CONSTRUCTION | 4.62 | 0 | 0 | 50
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. | SM/13996 | Augmentation | Formal work order for the construction of Pump House, Vertical extension of Boundary wall and Pump House repairing , Laying Distribution System, Rising Main Connection for Augmentation of PUTIA ( ZONE-I ) Ground water based Piped water supply scheme Raghunathganj -II Block under Murshidabad Division, P.H.E. Dte. [ (i)Amount for LDS, R.Main : Rs. 1,47,25,982.00 & (ii) Amount for Vertical B.Wall Extention & P.House Repairing : Rs. 13,13,446.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000810/2022-2023 | 810/MURD | 22/03/2023 | 01/03/2025 | JAYANTA KUMAR CHANDRA | 160.12 | 87.97 | 54.94 | 50
Total | [13 empty] | 447.85 | 161.82 | 36.13