## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/13997 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000205/2023-2024 | 1210/MURD/20 | 02/05/2023 | 02/05/2023 | Resource Division | 27.82 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/13997 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II, Zone-I under RATURI ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000131/2023-2024 | 1918/MEDB | 16/06/2023 | 16/09/2023 | MENAKA ENTERPRISE | 20.8 | 9.15 | 43.97 | 5
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/13997 | Augmentation | Allied work for Road restoration damaged during laying of pipeline of Raturi Zone-I Piped Water Supply Scheme, Suti Block, Jangipur Sub-Division under Murshidabad Division, P.H.E dte. | ASSISTANT ENGINEER |  | ORD/000826/2023-2024 | 769/MURD | 13/03/2024 | 12/04/2024 | S. DUTTA | 48.28 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/13997 | Augmentation | Sinking of 1NO. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Raturi Zone-I Water Supply Scheme at Suti-I Block of Jangipur Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000170/2024-2025 | 2957/MURD | 11/11/2024 | 26/11/2024 | GAYEN ENTERPRISE | 11.73 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/13997 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at RATURI ZONE -I Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000713/2023-2024 | 3838/MURD | 14/12/2023 | 04/01/2024 | SUJIT KUMAR SAHA | 11.79 | 8.82 | 74.77 | 50
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/13997 | Augmentation | Sinking of 2NOS. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Raturi Zone-II Water Supply Scheme and Bahutuli Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000105/2024-2025 | 2195/MURD | 31/07/2024 | 30/08/2024 | SARKAR WATER SUPPLY AGENCY | 23.56 | 9.8 | 41.6 | 50
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/13997 | Augmentation | Rectification work from Raturi to Kalinagar in the road of Dangapara more to Raturi via HILORA, Kalinagar Road under berhampore Division-I PWD during the year of 2023-2024. |  |  | BILL/01020/2023-2024 | 468-MSD/2023-24 | 04/01/2024 | 04/01/2024 | EXECUTIVE ENGINEER, PWD, BERHAMPORE DIVISION-I | 78.16 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/13997 | Augmentation | Laying of distribution system for Augmentation work of RATURI ZONE I Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000856/2022-2023 | 792/MURD | 21/03/2023 | 12/03/2025 | S. DUTTA | 56.15 | 17.56 | 31.27 | 30
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/13997 | Augmentation | Providing FHTC of 1415 nos. household, Laying of Rising Main, Repair & Renovation of RCC 130 Cum OHR, special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works Augmentation work of Raturi (Zone-I) PWSS in SUTI-I Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000085/2023-2024 | 1455/MURD | 01/06/2023 | 28/11/2023 | R.M. BHATTA | 91.23 | 12.74 | 13.97 | 15
10 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/13997 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 09/06/2022 | RADIANT | 73.97 | 3.21 | 4.33 | 100
Total | [13 empty] | 443.49 | 61.27 | 13.81