## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | TENTULIA AND ADJOINING MOUJAS PWSS | SM/13998 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 1067/MURD/8 | 18/04/2023 |  | Resource Division | 1.31 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Berhampore Mechanical | TENTULIA AND ADJOINING MOUJAS PWSS | SM/13998 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under TENTULIA ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000160/2023-2024 | 2018/MEDB | 19/06/2023 | 17/09/2023 | S. G. ENTERPRISE | 20.29 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Berhampore Mechanical | TENTULIA AND ADJOINING MOUJAS PWSS | SM/13998 | New | AT TENTULIA PH 1 ID 304239411 |  |  | BILL/01472/2023-2024 | 361/WBSEDCL-JJM | 20/02/2024 |  | WBSEDCL | 3.48 | 0 | 0 | 0
4 | MURSHIDABAD | Kandi | Berhampore Mechanical | TENTULIA AND ADJOINING MOUJAS PWSS | SM/13998 | New | AT TENTULIA PH 1 ID 304239411 |  |  | BILL/01472/2023-2024 | 361/WBSEDCL-JJM | 20/02/2024 |  | WBSEDCL | 3.48 | 0 | 0 | 0
5 | MURSHIDABAD | Kandi | Murshidabad Division | TENTULIA AND ADJOINING MOUJAS PWSS | SM/13998 | New | Formal work order for the work of TENTULIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall, IEP and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000708/2022-2023 | 122/MURD | 13/01/2023 | 13/01/2024 | SOUNAK ENTERPRISE | 271.09 | 9.19 | 3.39 | 10
Total | [13 empty] | 299.67 | 9.19 | 3.07