## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Berhampore Mechanical | EROALI AND ADJOINING MOUJAS PWSS | SM/14236 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under EROALI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000667/2023-2024 | 3788/MEDB | 03/11/2023 | 03/02/2024 | DEBJYOTI BASU | 35.17 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Murshidabad Division | EROALI AND ADJOINING MOUJAS PWSS | SM/14236 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1004/MURD/11 | 17/04/2023 | 17/04/2023 | Resource Division | 47.05 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Murshidabad Division | EROALI AND ADJOINING MOUJAS PWSS | SM/14236 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 0 | 0 | 80
4 | MURSHIDABAD | Khargram | Murshidabad Division | EROALI AND ADJOINING MOUJAS PWSS | SM/14236 | New | Material Requisition To Resource Division |  |  | RTOR000369/2023-2024 | MURD/439/1 | 08/02/2024 | 08/02/2024 | Resource Division | 27.28 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | EROALI AND ADJOINING MOUJAS PWSS | SM/14236 | New | Eroali PH-1 Application No- 3004536843 |  |  | BILL/01177/2023-2024 | 241/WBSEDCL-JJM | 15/01/2024 | 15/01/2024 | WBSEDCL | 3.74 | 0 | 0 | 0
6 | MURSHIDABAD | Khargram | Berhampore Mechanical | EROALI AND ADJOINING MOUJAS PWSS | SM/14236 | New | POWER CONNECTION AT PWSS PH 2 EROLI ID 304250314 |  |  | BILL/00182/2024-2025 | 45/WBSEDCL-JJM | 22/04/2024 | 22/04/2024 | WBSEDCL | 4.22 | 0 | 0 | 0
7 | MURSHIDABAD | Khargram | Berhampore Mechanical | EROALI AND ADJOINING MOUJAS PWSS | SM/14236 | New | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Khargram and Nawda block Under District Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000053/2025-2026 | 45/4 | 29/05/2025 | 29/08/2025 | EASTERN INDIA SALES & SERVICE | 15.17 | 0 | 0 | 0
8 | MURSHIDABAD | Khargram | Murshidabad Division | EROALI AND ADJOINING MOUJAS PWSS | SM/14236 | New | Formal work order for the work of EROALI & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362274S000) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000711/2022-2023 | 90/MURD | 11/01/2023 | 01/05/2025 | M/S. S. DAS AND ENTERPRISE | 833.44 | 0 | 0 | 38
Total | [13 empty] | 1063.56 | 0 | 0