## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | PETARI AND ADJOINING MOUJAS PWSS | SM/14237 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1004/MURD/16 | 17/04/2023 | 17/04/2023 | Resource Division | 23.72 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Berhampore Mechanical | PETARI AND ADJOINING MOUJAS PWSS | SM/14237 | New | Electric Service New Connection PETARI PH- 2 PWSS Application NO. 3004404553. ID. 304120628 |  |  | BILL/01034/2023-2024 | 169/WBSEDCL-JJM | 05/12/2023 | 05/12/2023 | WBSEDCL | 3.13 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | PETARI AND ADJOINING MOUJAS PWSS | SM/14237 | New | Electric Service New Connection PETARI PH-1 PWSS Application NO. 3004494692. ID. 304193611 |  |  | BILL/01035/2023-2024 | 170/WBSEDCL-JJM | 05/12/2023 | 05/12/2023 | WBSEDCL | 6.35 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | PETARI AND ADJOINING MOUJAS PWSS | SM/14237 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under PETARI ground water based water supply scheme under Block_ BURWAN, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000157/2023-2024 | 2085/MEDB | 19/06/2023 | 31/12/2025 | JOGMAYA ENGINEERING | 23.47 | 19.34 | 82.39 | 20
5 | MURSHIDABAD | Burwan | Murshidabad Division | PETARI AND ADJOINING MOUJAS PWSS | SM/14237 | New | Formal work order for the work of PETARI & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362276S000) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000717/2022-2023 | 79/MURD | 10/01/2023 | 01/01/2026 | MAMATA USHA ENTERPRISE | 754.5 | 494.64 | 65.56 | 60
Total | [13 empty] | 811.17 | 513.97 | 63.36