## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Berhampore Mechanical | KUMAR SANDA AND ADJOINING MOUJAS PWSS | SM/14238 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II and III under KUMAR SANDA ground water based water supply scheme under Block_ KANDI Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000151/2023-2024 | 2082/MEDB | 19/06/2023 | 19/09/2023 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 36.82 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Murshidabad Division | KUMAR SANDA AND ADJOINING MOUJAS PWSS | SM/14238 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1043/MURD/9 | 17/04/2023 | 17/04/2023 | Resource Division | 32.79 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Murshidabad Division | KUMAR SANDA AND ADJOINING MOUJAS PWSS | SM/14238 | New | Formal work order for the work of KUMAR SANDA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362351S000) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3 | ORD/000713/2022-2023 | 92/MURD | 11/01/2023 | 01/01/2026 | ACQUA CONSTRACTION CONSORTIAM | 678.7 | 0 | 0 | 20
Total | [13 empty] | 748.32 | 0 | 0