## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS | SM/14495 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1210/MURD/35 | 02/05/2023 | 02/05/2023 | Resource Division | 21.05 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS | SM/14495 | New | Formal work order for Laying Distribution System (PART-C), FHTC (PART-C), for Uncovered of AMJUA PWSS at AMJUA ( Village Code-315107) , CHURIGRAM ( Village Code-315108) , DURGARAMPUR ( Village Code-315109) in Khargram Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000730/2022-2023 | 339/MURD | 08/02/2023 | 09/05/2023 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 146.33 | 77.64 | 53.06 | 34
3 | MURSHIDABAD | Khargram | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS | SM/14495 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 0 | 0 | 80
4 | MURSHIDABAD | Khargram | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS | SM/14495 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia Replacement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AMJUA PWSS at Head Work Site & 2nd Tube Well Site in Khargram Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000657/2022-2023 | 380/MURD | 10/02/2023 | 27/03/2023 | SUJIT KUMAR SAHA | 16.81 | 14.08 | 83.75 | 100
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | AMJUA AND ADJOINING MOUJAS PWSS | SM/14495 | New | NEW SERVICE CONNECTION AT AMJUA PH1 ID 304158525 |  |  | BILL/01129/2023-2024 | 220/WBSEDCL-JJM | 05/01/2024 | 05/01/2024 | WBSEDCL | 8.29 | 0 | 0 | 0
6 | MURSHIDABAD | Khargram | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS | SM/14495 | New | Formal work order for Laying Distribution System (PART-B), FHTC (PART-B), Boundary wall for Uncovered of AMJUA PWSS at UTTAR GANGARAMPUR ( Village Code-315100) , SADAL ( Village Code-315101) , BHAT KANDA ( Village Code-315102) in Khargram Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. [(i)Amount for LDS & FHTC: Rs.2,54,73,199.00 & (ii) Amount for Boundwary Wall: Rs. 31,33,915.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000759/2022-2023 | 453/MURD | 17/02/2023 | 04/10/2025 | PRADIP KUMAR DAS | 285.93 | 31.09 | 10.87 | 5
7 | MURSHIDABAD | Khargram | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS | SM/14495 | New | Formal work order for Construction of 400 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, FHTC (PART-A), for Uncovered of AMJUA PWSS at RAHIGRAM Village in Khargram Block, Kandi Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000748/2022-2023 | 414/MURD | 15/02/2023 | 01/04/2026 | M/S.TAPAS KUMAR CHAKRABORTY | 306.3 | 68.67 | 22.42 | 10
8 | MURSHIDABAD | Khargram | Berhampore Mechanical | AMJUA AND ADJOINING MOUJAS PWSS | SM/14495 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under AMJUA ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000078/2023-2024 | 3787/MEDB | 03/11/2023 | 15/06/2028 | KASHINATH PAL & CO. | 24.35 | 0 | 0 | 40
Total | [13 empty] | 906.53 | 191.49 | 21.12