## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1210/MURD/33 | 02/05/2023 | 02/05/2023 | Resource Division | 24.92 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | Retrofitting Functional Household Tap Connection (FHTC) under Jal Jeevan Mission for command area of Uncovered BATI Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000706/2022-2023 | 120/MURD | 13/01/2023 | 12/02/2023 | DEBASIS BOSE | 71.38 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bati & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K a n d i Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000046/2023-2024 | 1216/MURD | 03/05/2023 | 02/06/2023 | MAMATA USHA ENTERPRISE | 21.38 | 11.25 | 52.62 | 50
4 | MURSHIDABAD | Kandi | Berhampore Mechanical | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BATI ground water based water supply scheme under Block_ KANDI Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000668/2023-2024 | 4292/MEDB | 29/12/2023 | 29/03/2024 | DAS ENTERPRISE ( MANGO LANE) | 22.1 | 0 | 0 | 0
5 | MURSHIDABAD | Kandi | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | Material Requisition To Resource Division |  |  | RTOR000368/2023-2024 | MURD/439/12 | 08/02/2024 | 08/02/2024 | Resource Division | 8.91 | 0 | 0 | 0
6 | MURSHIDABAD | Kandi | Berhampore Mechanical | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | new service connection at BATI PH1 ID304200864,Application no.3004504556 |  |  | BILL/01145/2023-2024 | 219/WBSEDCL-JJM | 05/01/2024 | 05/01/2024 | WBSEDCL | 8.77 | 0 | 0 | 0
7 | MURSHIDABAD | Kandi | Berhampore Mechanical | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | NEW SERVICE CONNECTION AT BATI PH 2 CID 304252900 |  |  | BILL/01492/2023-2024 |  | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.01 | 0 | 0 | 0
8 | MURSHIDABAD | Kandi | Berhampore Mechanical | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | AT BATI PH 2 ID 304252900 |  |  | BILL/01467/2023-2024 | 376/WBSEDCL-JJM | 21/02/2024 | 21/02/2024 | WBSEDCL | 3.01 | 0 | 0 | 0
9 | MURSHIDABAD | Kandi | Berhampore Mechanical | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | SHIFTING OF A PART OF EXISTING HTOH LINE AT BATI PWSS ID860318411 |  |  | BILL/01113/2024-2025 |  | 25/11/2024 | 25/11/2024 | WBSEDCL | 0.57 | 0 | 0 | 0
10 | MURSHIDABAD | Kandi | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | Formal Work Order for construction of 200 Cum OHR,,Laying Distribution System (PART-A),Rising Main Connection, Boundwary Wall, for Uncovered of BATI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division , PHE.Dte. [(i)Amount for LDS , R.Main: Rs.1,64,06,836.00 & (ii) Amount for OHR & B. Wall : Rs. 1,25,46,499.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000766/2022-2023 | 484/MURD | 20/02/2023 | 01/01/2026 | AJAY MONDAL | 289.48 | 74.39 | 25.7 | 30
11 | MURSHIDABAD | Kandi | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | Laying Distribution System (PART-B), Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) for Uncoveded BATI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte.for [ (i) Amount for Laying Distribution System: Rs.72,79,775.00 & (ii) Amount for Pump House: Rs. 10,55,058.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000720/2022-2023 | 121/MURD | 13/01/2023 | 30/04/2025 | M/S. GOURI ENTERPRISE | 84.16 | 72.71 | 86.4 | 50
12 | MURSHIDABAD | Kandi | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Kandi Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(89 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000133/2024-2025 | 2635/MURD | 23/09/2024 | 01/07/2025 | SABSAMAY | 9.85 | 0 | 0 | 80
13 | MURSHIDABAD | Kandi | Berhampore Mechanical | BATI AND IT'S ADJOINING MOUJAS PWSS | SM/14496 | New | SHIFTING OF A PART OF EXISTING HTOH LINE AT BATI PWSS ID860318411 |  |  | BILL/01127/2024-2025 | 273/WBSEDCL-JJM | 28/11/2024 | 28/11/2024 | WBSEDCL | 0.57 | 0 | 0 | 0
Total | [13 empty] | 548.1 | 158.35 | 28.89