## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS | SM/14503 | New | Material Requisition To Resource Division |  |  | RTOR000274/2023-2024 | 1230/MURD/17 | 04/05/2023 |  | Resource Division | 2.89 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Berhampore Mechanical | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS | SM/14503 | New | NEW SERVICE CONNECTION AT PWSS PH1 GOURINAGAR ID 304248173 |  |  | BILL/01427/2023-2024 | 317/WBSEDCL-JJM | 05/02/2024 |  | WBSEDCL | 8.13 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS | SM/14503 | New | NEW SERVICE CONNECTION AT PWSS PH1 GOURINAGAR ID 304248173 |  |  | BILL/01427/2023-2024 | 317/WBSEDCL-JJM | 05/02/2024 |  | WBSEDCL | 8.13 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS | SM/14503 | New | NEW SERVICE CONNECTION AT PWSS GOURINAGAR PH2 ID 304247757 |  |  | BILL/01428/2023-2024 | 318/WBSEDCL-JJM | 05/02/2024 |  | WBSEDCL | 6.9 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Berhampore Mechanical | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS | SM/14503 | New | NEW SERVICE CONNECTION AT PWSS GOURINAGAR PH2 ID 304247757 |  |  | BILL/01428/2023-2024 | 318/WBSEDCL-JJM | 05/02/2024 |  | WBSEDCL | 6.9 | 0 | 0 | 0
6 | MURSHIDABAD | Burwan | Berhampore Mechanical | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS | SM/14503 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for NEWLY SUNK TUBE WELL in connection to Accommodate FHTC at Pump House No.-I & II under GOURI NAGAR ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001427/2023-2024 | 4341/MEDB | 29/12/2023 | 28/03/2024 | M/S S. S. ENTERPRISE (DOMKAL) | 18.46 | 0 | 0 | 0
7 | MURSHIDABAD | Burwan | Murshidabad Division | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS | SM/14503 | New | Formal work order for GOURI NAGAR & adjoining mouzas PWSS to accommodate FHTC under Jal Jiban Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000798/2022-2023 | 607/MURD | 02/03/2023 | 07/12/2023 | ABDUL JABBAR DEWAN | 218.13 | 70.67 | 32.4 | 65
Total | [13 empty] | 269.52 | 70.67 | 26.22