## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | JHILLI AND ADJOINING MOUJAS PWSS | SM/14505 | New | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 1067/MURD/1 | 18/04/2023 | 18/04/2023 | Resource Division | 21.94 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Berhampore Mechanical | JHILLI AND ADJOINING MOUJAS PWSS | SM/14505 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at P.H. No.-I & II under JHILLI ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000708/2023-2024 | 4061/MEDB | 04/12/2023 | 04/03/2024 | SREE RADHA ELECTRICAL | 24.06 | 0 | 0 | 50
3 | MURSHIDABAD | Khargram | Berhampore Mechanical | JHILLI AND ADJOINING MOUJAS PWSS | SM/14505 | New | NEW SERVICE CONNECTION AT JHILLI PH 2 ID 304171278 |  |  | BILL/01127/2023-2024 | 218/WBSEDCL-JJM | 05/01/2024 | 05/01/2024 | WBSEDCL | 10.53 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Berhampore Mechanical | JHILLI AND ADJOINING MOUJAS PWSS | SM/14505 | New | NEW SERVICE CONNECTION AT JHILLI PWSS PH1 ID304171275 |  |  | BILL/01126/2023-2024 | 217/WBSEDCL-JJM | 05/01/2024 | 05/01/2024 | WBSEDCL | 6.95 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Murshidabad Division | JHILLI AND ADJOINING MOUJAS PWSS | SM/14505 | New | Formal work order for the work of JHILLI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000700/2022-2023 | 123/MURD | 16/01/2023 | 01/06/2025 | M/S RUBIET HOSSAIN | 616.31 | 0 | 0 | 10
Total | [13 empty] | 679.79 | 0 | 0