## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/14722 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER |  | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 04/04/2022 | MERCHANDISE-INDIA | 105.32 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/14722 | Augmentation | Formal work order for the Work of Augmentation of Dhulauri Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 3 | ORD/000703/2022-2023 | 350/MURD | 08/02/2023 | 07/08/2023 | M/S. S. DAS AND ENTERPRISE | 419.15 | 0 | 0 | 48
3 | MURSHIDABAD |  | Murshidabad Division | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/14722 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000304/2023-2024 | 1278/MURD/13 | 10/05/2023 | 10/05/2023 | Resource Division | 34.6 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/14722 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under DHULAURI ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II | ORD/000688/2023-2024 | 4295/MEDB | 29/12/2023 | 29/03/2024 | SUBHRA ENTERPRISE | 22.13 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/14722 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dhulauri Water Supply Scheme and Tejsinghapur Water Supply Schem under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER_DOMKAL BLOCK | ORD/000104/2023-2024 | 1746/MURD | 06/07/2023 | 27/07/2023 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 0 | 100
Total | [13 empty] | 604.79 | 0 | 0