## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/14828 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 04/04/2022 | SAI GEOMETRIC SOLUTION | 28.62 | 0 | 0 | 100
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/14828 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000235/2023-2024 | 1219/MURD/15 | 03/05/2023 | 03/05/2023 | Resource Division | 26 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/14828 | Augmentation | Augmentation of MURADPUR JALANGI ZONE-I PWSS Laing Distribution System, Rising Main Connection Repairing P.H, B.W, Construction of P.H of JALANGI Block , under Murshidabad Division PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000531/2023-2024 | 3114/MURD | 05/10/2023 | 31/03/2025 | ARINDAM MAJUMDAR | 187.44 | 0 | 0 | 60
4 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/14828 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000539/2024-2025 | 325/MEDB | 10/02/2025 | 10/05/2025 | JOY BISHNU ENGINEERING CO. | 11.35 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/14828 | Augmentation | Refilling of sand layers, Activated Alumina & existing gravel after washing along with allied works of AIRP at Saikhpara Area (Capacity 100 Cum/hr.) & Muradpur Jalangi Z-I (Capacity 54.00 Cum/hr.) Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000842/2023-2024 | 820/MURD | 15/03/2024 | 14/11/2024 | M/S. S. DAS AND ENTERPRISE | 70.68 | 0 | 0 | 40
Total | [13 empty] | 324.09 | 0 | 0