## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | Augmentation | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chumarigacha (Village code 315340) under Basabari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723194 in the District of Murshidabad | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000725/2020-2021 | 3122 / MURD | 09/12/2020 | 07/02/2021 | TANUSHREE ENTERPRISE | 39.34 | 1.16 | 2.96 | 1
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BASABARI & CHHAIGHARI Water Supply Scheme at Head work site at BERHAMPORE Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000723/2023-2024 | 3875/MURD | 18/12/2023 | 08/01/2024 | NADIA TUBEWELLS | 11.78 | 9.22 | 78.24 | 100
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | Augmentation | BASABARI PH-1 |  |  | BILL/01520/2023-2024 | 402/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 4.36 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B |  | JUNIOR ENGINEER 1,JUNIOR ENGINEER_BERHAMPORE BLOCK | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 04/04/2022 | ENVIROTECH SOLUTIONS | 32.69 | 4.3 | 13.16 | 1
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | Augmentation | Augmentation of Ground Water Based Basabari PWSS to accommodate FHTC of 673 nos household Laying Rising Main , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works, Construction of Boundary Wall of 270 m and Soil Investigation & 250 Cum Construction of OHR at Berhampore Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000550/2023-2024 | 3180/MURD | 11/10/2023 | 10/10/2025 | SAMBHU NATH ROY | 223.72 | 13.35 | 5.97 | 10
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | Augmentation | Water Supply arrangmenet for arsenic affected habitation with SOLAR Power connection at different block under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad. (PART-C). | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000593/2020-2021 | 503/MURD | 02/02/2021 | 03/04/2021 | PAL TROCKNER (P) LTD. | 37.91 | 0 | 0 | 100
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 19/12/2024 | SUJIT MONDAL | 7.27 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | Augmentation | Laying of Distribution System including Refixing the existing FHTCs connection on new distribution system of Basabari Ground Based piped water supply scheme of in Berhampore Block of Berhampore Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000419/2024-2025 | 511/MURD | 28/02/2025 | 29/04/2025 | M/S. M.G. CONSTRUCTION | 40.27 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | Augmentation | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 01/08/2025 | M/S. BIMALENDU BOSE | 46.93 | 0 | 0 | 75
10 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | Augmentation | Laying Distribution System For Augmentation of Basabari (Part-A) PWSS of Berhampore Block under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000769/2022-2023 | 496/MURD | 21/02/2023 | 17/02/2025 | SANDHAN ADHIKARI | 73.69 | 55.37 | 75.14 | 85
11 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/14830 | Augmentation | Construction of Pump House cum Chlorine Room with sanitary and Water Supply Arrangement at Basabari PWSS at Berhampore Block under Berhampore Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000058/2024-2025 | 1989/MURD | 08/07/2024 | 10/01/2025 | ANIRBAN CHATTERJEE | 7.39 | 0 | 0 | 100
Total | [13 empty] | 525.34 | 83.41 | 15.88