## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | HAMIDPUR AND ADJOINING MOUJAS PWSS | SM/14867 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 1075/MURD/12 | 19/04/2023 | 19/04/2023 | Resource Division | 1.09 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | HAMIDPUR AND ADJOINING MOUJAS PWSS | SM/14867 | New | NEW CONNECTION AT HAMIDPUR PH-II |  |  | BILL/00402/2024-2025 | 107/WBSEDCL-JJM | 05/06/2024 | 05/06/2024 | WBSEDCL | 8.94 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | HAMIDPUR AND ADJOINING MOUJAS PWSS | SM/14867 | New | NEW CONNECTION AT HAMIDPUR PH-I |  |  | BILL/00401/2024-2025 | 106/WBSEDCL-JJM | 05/06/2024 | 05/06/2024 | WBSEDCL | 9.71 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | HAMIDPUR AND ADJOINING MOUJAS PWSS | SM/14867 | New | HAMIDPUR & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BHARATPUR-I of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000872/2022-2023 | 872/MURD | 27/03/2023 | 31/07/2025 | PRATIMA CONSTRUCTION | 159.76 | 79.99 | 50.07 | 5
5 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | HAMIDPUR AND ADJOINING MOUJAS PWSS | SM/14867 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Hamidpur ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000270/2023-2024 | 3707/MEDB | 03/11/2023 | 03/11/2026 | CONCORD ENGINEERING | 23.56 | 0 | 0 | 10
Total | [13 empty] | 203.06 | 79.99 | 39.39