## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | BIPRA SEKHAR AND ADJOING MOUJAS PWSS | SM/14868 | New | Material Requisition To Resource Division |  |  | RTOR000234/2023-2024 | 1219/MURD/11 | 03/05/2023 |  | Resource Division | 21.03 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Berhampore Mechanical | BIPRA SEKHAR AND ADJOING MOUJAS PWSS | SM/14868 | New | NEW SERVICE CONNECTION AT PWSS BIPRASEKHAR PH1 ID 304247611 |  |  | BILL/01425/2023-2024 | 315/WBSEDCL-JJM | 05/02/2024 |  | WBSEDCL | 9.43 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | BIPRA SEKHAR AND ADJOING MOUJAS PWSS | SM/14868 | New | NEW SERVICE CONNECTION AT PWSS BIPRASEKHAR PH1 ID 304247611 |  |  | BILL/01425/2023-2024 | 315/WBSEDCL-JJM | 05/02/2024 |  | WBSEDCL | 9.43 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | BIPRA SEKHAR AND ADJOING MOUJAS PWSS | SM/14868 | New | NEW SERVICE CONNECTION AT PWSS PH 2 BIPRASEKHAR ID 304247692 |  |  | BILL/01426/2023-2024 | 316/WBSEDCL-JJM | 05/02/2024 |  | WBSEDCL | 7.95 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Berhampore Mechanical | BIPRA SEKHAR AND ADJOING MOUJAS PWSS | SM/14868 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Bipra Sekhar ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000265/2023-2024 | 3702/MEDB | 03/11/2023 | 01/02/2024 | M/S S. S. ENTERPRISE (DOMKAL) | 22.55 | 0 | 0 | 50
6 | MURSHIDABAD | Burwan | Murshidabad Division | BIPRA SEKHAR AND ADJOING MOUJAS PWSS | SM/14868 | New | BIPRA SEKHAR PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Burwan Block , Kandi Sub-Division, of Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000863/2022-2023 | 823/MURD | 23/03/2023 | 22/03/2024 | DILIP KUMAR MONDAL | 657.71 | 233.73 | 35.54 | 50
7 | MURSHIDABAD | Burwan | Murshidabad Division | BIPRA SEKHAR AND ADJOING MOUJAS PWSS | SM/14868 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BIPRA SEKHAR AND ADJOINING MOUJAS Water Supply Scheme & ALAMPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000400/2023-2024 | 2807/MURD | 05/09/2023 | 26/09/2023 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0 | 100
Total | [13 empty] | 746.55 | 233.73 | 31.31