## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | MIRHATI AND ADJOINING MOUJAS PWSS | SM/14869 | New | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 1129/MURD/7 | 25/04/2023 | 25/04/2023 | Resource Division | 1.09 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Berhampore Mechanical | MIRHATI AND ADJOINING MOUJAS PWSS | SM/14869 | New | Electric Service Connection at MIRHATI PWSS PH I, Application NO.3004467235, ID 304171280 |  |  | BILL/01069/2023-2024 | 190/WBSEDCL-JJM | 19/12/2023 | 19/12/2023 | WBSEDCL | 6.97 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Murshidabad Division | MIRHATI AND ADJOINING MOUJAS PWSS | SM/14869 | New | Material Requisition To Resource Division |  |  | RTOR000340/2023-2024 | 79/MURD/07 | 09/01/2024 | 09/01/2024 | Resource Division | 3.63 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Murshidabad Division | MIRHATI AND ADJOINING MOUJAS PWSS | SM/14869 | New | Material Requisition To Resource Division |  |  | RTOR000358/2023-2024 | MURD/439/03 | 08/02/2024 | 08/02/2024 | Resource Division | 0.13 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | MIRHATI AND ADJOINING MOUJAS PWSS | SM/14869 | New | NEW SERVICE CONNECTION AT PH2 MIRHATI ID304239447 |  |  | BILL/01411/2023-2024 | 308/WBSEDCL-JJM | 05/02/2024 | 05/02/2024 | WBSEDCL | 4.81 | 0 | 0 | 0
6 | MURSHIDABAD | Khargram | Murshidabad Division | MIRHATI AND ADJOINING MOUJAS PWSS | SM/14869 | New | Formal work order for Laying Distribution System of MIRHATI PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Murshidabad Circle ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000854/2022-2023 | 789/MURD | 21/03/2023 | 01/04/2025 | SUBHANKAR ROY | 139.07 | 0 | 0 | 30
7 | MURSHIDABAD | Khargram | Berhampore Mechanical | MIRHATI AND ADJOINING MOUJAS PWSS | SM/14869 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under MIRHATI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000273/2023-2024 | 3713/MEDB | 03/11/2023 | 01/01/2026 | B. T. PROJECTS PVT. LTD. | 21.24 | 0 | 0 | 70
Total | [13 empty] | 176.95 | 0 | 0