## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 09/06/2022 | RADIANT | 73.97 | 3.25 | 4.39 | 100
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | Augmentation | Laying of Rising Main & Distribution System for Augmentation of FATELLAPUR Piped Water Supply in SUTI-I Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000839/2022-2023 | 743/MURD | 16/03/2023 | 10/05/2026 | RAJU ENTERPRISE | 66.32 | 32.52 | 49.03 | 36
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | Augmentation | Providing FHTC Connection to 1823 no household, Overhauling of RCC 350 Cum OHR & Repair of Boundary Wall =150 m at T/W-I site & T/W-II site for Augmentation of FATELLAPUR Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000878/2022-2023 | 903/MURD | 29/03/2023 | 25/09/2023 | M/S M.S. ENTERPRISE | 106.37 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under FATELLAPUR ground water based water supply scheme under Block_ Suti-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000670/2023-2024 | 4294/MEDB | 29/12/2023 | 27/03/2026 | WEST BENGAL ENGINEERING CO. | 33.56 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at FATELLAPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000712/2023-2024 | 3837/MURD | 14/12/2023 | 04/01/2024 | SUJIT KUMAR SAHA | 11.79 | 0 | 0 | 100
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 1210/MURD/18 | 02/05/2023 | 02/05/2023 | Resource Division | 24.99 | 0 | 0 | 0
7 | MURSHIDABAD |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 23/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 7.33 | 1.6 | 10
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | Augmentation | Sinking of 1NO. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Fatellapur Water Supply Scheme at Suti-I Block of Jangipur Sub-Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000098/2024-2025 | 2131/MURD | 26/07/2024 | 07/03/2025 | KHOKAN BISWAS | 11.76 | 0 | 0 | 100
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 60 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for FATELLAPUR Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000038/2025-2026 | 1155/MURD | 20/05/2025 | 19/07/2025 | WATER TECH | 33.62 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | Augmentation | NEW CONNECTION AT FATELLAPUR PH-2 |  |  | BILL/01420/2024-2025 | 379/WBSEDCL-JJM | 04/02/2025 | 04/02/2025 | WBSEDCL | 4.43 | 0 | 0 | 0
11 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/14942 | Augmentation | NEW CONNECTION AT FATELLAPUR PH-1 |  |  | BILL/01419/2024-2025 | 378/WBSEDCL-JJM | 04/02/2025 | 04/02/2025 | WBSEDCL | 5.73 | 0 | 0 | 0
Total | [13 empty] | 831.24 | 43.09 | 5.18