## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. | SM/14943 | Augmentation | Repair of Pump Houses , Construction of toilet , Reinforced Barbed Tape (R.B.T) Concertina fencing on Boundary wall top & approach road for JAGTAI Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte.in the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000637/2022-2023 | 3167/MURD | 30/11/2022 | 30/12/2022 | M/S JOY MA BANAMALI | 7.11 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. | SM/14943 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 0 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. | SM/14943 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000224/2023-2024 | 1219/MURD/29 | 03/05/2023 | 03/05/2023 | Resource Division | 18.03 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. | SM/14943 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2024-2025 | MURD/2991 | 13/11/2024 | 13/11/2024 | Resource Division | 25.25 | 0 | 0 | 0
5 | MURSHIDABAD |  | Central Drilling | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. | SM/14943 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. | SM/14943 | Augmentation | Augmentation Work of Jagtai Piped Water Supply Scheme to accommodate with FHTC (1730 Nos), Laying of Rising Main , Laying of Distribution System , construction of 200 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3,JUNIOR ENGINEER 6 | ORD/000314/2023-2024 | 2670/MURD | 24/08/2023 | 23/08/2025 | GREENLEAF CONSTRUCTION | 336.47 | 0 | 0 | 40
Total | [13 empty] | 21808.05 | 0 | 0