## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 0 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 1167/MURD/47 | 28/04/2023 | 28/04/2023 | Resource Division | 11.06 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 1210/MURD/23 | 02/05/2023 | 02/05/2023 | Resource Division | 4.02 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Providing FHTC Connection to 650 nos household , Repairing & Vertical Extention of Boundary Wall ,Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement & Pump House repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity of staging height 20 mtr. (Shaft wall ) for Augmentation work of Basudebpur (Zone-I) PWSS in Samsherganj Block under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000787/2022-2023 | 541/MURD | 24/02/2023 | 10/03/2026 | MOLLA ENTERPRISE | 49.98 | 0 | 0 | 25
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Laying of Distribution System for Augmentation work of Basudebpur(Zone-I) PWSS in Samsherganj Block under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000893/2022-2023 | 902/MURD | 29/03/2023 | 18/03/2025 | JAI BHARAT COMMERCIAL CORPORATION | 112.15 | 0 | 0 | 40
6 | MURSHIDABAD |  | Central Drilling | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Balance work of Laying of UPVC Pipe , Construction of approach road , Modification of R.C.C. Elevated Reservoir and Pump House, Boundary wall, for Augmentation of Basudevpur (Zone-I) Water Supply Scheme in Suti-I Block of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000242/2024-2025 | 191/MURD | 21/01/2025 | 01/09/2025 | MOLLA ENTERPRISE | 40.58 | 0 | 0 | 35
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for BASUDEBPUR Zone ¿I Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000021/2025-2026 | 986/MURD | 02/05/2025 | 01/07/2025 | J.S. CONSTRUCTION | 23.01 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Basudevpur Halt Station to Dhulianganga Station (TP NO 235/2 & 235/3) at Basudevpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Basudevpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000426/2021-2022 | 2483/MURD | 16/08/2021 | 15/10/2021 | SANJAY BISWAS | 22.75 | 0 | 0 | 100
Total | [13 empty] | 21684.75 | 0 | 0