## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 1167/MURD/47 | 28/04/2023 |  | Resource Division | 11.06 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 1210/MURD/23 | 02/05/2023 |  | Resource Division | 4.02 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Basudevpur Halt Station to Dhulianganga Station (TP NO 235/2 & 235/3) at Basudevpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Basudevpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000426/2021-2022 | 2483/MURD | 16/08/2021 | 15/10/2021 | SANJAY BISWAS | 22.75 | 14.61 | 64.2 | 100
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 0 | 100
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Laying of Distribution System for Augmentation work of Basudebpur(Zone-I) PWSS in Samsherganj Block under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000893/2022-2023 | 902/MURD | 29/03/2023 | 25/09/2023 | JAI BHARAT COMMERCIAL CORPORATION | 112.15 | 20.58 | 18.35 | 40
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Providing FHTC Connection to 650 nos household , Repairing & Vertical Extention of Boundary Wall ,Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement & Pump House repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity of staging height 20 mtr. (Shaft wall ) for Augmentation work of Basudebpur (Zone-I) PWSS in Samsherganj Block under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000787/2022-2023 | 541/MURD | 24/02/2023 | 23/08/2023 | MOLLA ENTERPRISE | 49.98 | 7.11 | 14.23 | 25
7 | MURSHIDABAD |  | Central Drilling | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/14944 | Augmentation | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 180 (One Hundred Eighty) Days].For the month of 16/07/2024 to 11/01/2025. [ Vehicle No:- WB 58 BU 9284] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6 | ORD/000087/2024-2025 | 48/JSD | 15/07/2024 | 11/01/2025 | ABIDA CONSTRUCTION | 0.88 | 0 | 0 | 0
Total | [13 empty] | 21622.05 | 42.29 | 0.2