## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. | SM/14946 | New | Formal work order for Laying Distribution system (PART-A) at SADPUR PWSS of Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000744/2022-2023 | 382/MURD | 10/02/2023 | 01/05/2025 | S.K. ENTERPRISE (SANDIP GHOSH) | 136.23 | 115.84 | 85.03 | 85
2 | MURSHIDABAD | Kandi | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. | SM/14946 | New | Formal work order for Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of SADPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362342S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,30,41,399.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,56,32,356.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000761/2022-2023 | 475/MURD | 20/02/2023 | 01/04/2025 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 286.71 | 69.44 | 24.22 | 21
3 | MURSHIDABAD | Kandi | Berhampore Mechanical | SADPUR PIPE WATER SUPPLY SCHEME. | SM/14946 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of SADPUR ground water based water supply scheme under Block- Kandi Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000102/2023-2024 | 3790/MEDB | 03/11/2023 | 01/09/2025 | S. P. CONSTRUCTION | 20.89 | 0 | 0 | 40
4 | MURSHIDABAD | Kandi | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. | SM/14946 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SADPUR PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000786/2022-2023 | 542/MURD | 24/02/2023 | 10/04/2023 | INDRAJIT MAZUMDAR | 16.8 | 14.61 | 86.96 | 80
5 | MURSHIDABAD | Kandi | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. | SM/14946 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1210/MURD/38 | 02/05/2023 | 02/05/2023 | Resource Division | 29.54 | 0 | 0 | 0
6 | MURSHIDABAD | Kandi | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. | SM/14946 | New | Material Requisition To Resource Division |  |  | RTOR000345/2023-2024 | 112/MURD/02 | 11/01/2024 | 11/01/2024 | Resource Division | 11.89 | 0 | 0 | 0
7 | MURSHIDABAD | Kandi | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. | SM/14946 | New | Material Requisition To Resource Division |  |  | RTOR000367/2023-2024 | MURD/439/11 | 08/02/2024 | 08/02/2024 | Resource Division | 5.94 | 0 | 0 | 0
8 | MURSHIDABAD | Kandi | Berhampore Mechanical | SADPUR PIPE WATER SUPPLY SCHEME. | SM/14946 | New | NEW SERVICE CONNECTION AT PH 1 SADPUR ID 304252899 |  |  | BILL/01465/2023-2024 | 360/WBSEDCL-JJM | 20/02/2024 | 20/02/2024 | WBSEDCL | 3.59 | 0 | 0 | 0
Total | [13 empty] | 511.6 | 199.89 | 39.07