## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1210/MURD/42 | 02/05/2023 | 02/05/2023 | Resource Division | 32.6 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Berhampore Mechanical | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MOLLA ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000101/2023-2024 | 1891/MEDB | 16/06/2023 | 31/07/2025 | S.P. ENTERPRISE (SILIGURI) | 23.4 | 0 | 0 | 30
3 | MURSHIDABAD | Kandi | Berhampore Mechanical | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | AT MOLLA PH2 ID 304252910 |  |  | BILL/01468/2023-2024 | 359/WBSEDCL-JJM | 20/02/2024 | 20/02/2024 | WBSEDCL | 5.41 | 0 | 0 | 0
4 | MURSHIDABAD | Kandi | Berhampore Mechanical | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | AT MOLLA PH 1 ID 304252903 |  |  | BILL/01466/2023-2024 | 358/WBSEDCL-JJM | 20/02/2024 | 20/02/2024 | WBSEDCL | 3.88 | 0 | 0 | 0
5 | MURSHIDABAD | Kandi | Murshidabad Division | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | Formal Work Order For Construction of 150 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of MOLLA PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362345S000) [(i)Amount for LDS , R.Main & FHTC: Rs.1,98,91,791.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs. 1,23,31,559.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000749/2022-2023 | 415/MURD | 15/02/2023 | 01/04/2026 | M/S NIRAPADA BHATTACHARJEE | 322.07 | 0 | 0 | 5
6 | MURSHIDABAD | Kandi | Murshidabad Division | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MOLLA PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division,P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer, Estimating Section | ORD/000742/2022-2023 | 381/MURD | 10/02/2023 | 27/03/2023 | NADIA TUBEWELLS | 16.81 | 0 | 0 | 95
Total | [13 empty] | 404.17 | 0 | 0