## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | Formal Work Order For Construction of 150 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of MOLLA PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362345S000) [(i)Amount for LDS , R.Main & FHTC: Rs.1,98,91,791.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs. 1,23,31,559.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000749/2022-2023 | 415/MURD | 15/02/2023 | 01/04/2026 | M/S NIRAPADA BHATTACHARJEE | 322.07 | 15.96 | 4.95 | 5
2 | MURSHIDABAD | Kandi | Berhampore Mechanical | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MOLLA ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000101/2023-2024 | 1891/MEDB | 16/06/2023 | 31/07/2025 | S.P. ENTERPRISE (SILIGURI) | 23.4 | 0 | 0 | 30
3 | MURSHIDABAD | Kandi | Murshidabad Division | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MOLLA PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division,P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer, Estimating Section | ORD/000742/2022-2023 | 381/MURD | 10/02/2023 | 27/03/2023 | NADIA TUBEWELLS | 16.81 | 15.53 | 92.39 | 95
4 | MURSHIDABAD | Kandi | Murshidabad Division | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1210/MURD/42 | 02/05/2023 | 02/05/2023 | Resource Division | 32.6 | 0 | 0 | 0
5 | MURSHIDABAD | Kandi | Murshidabad Division | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 28/07/2024 | IMAGIN | 95.53 | 3.79 | 3.97 | 100
6 | MURSHIDABAD | Kandi | Berhampore Mechanical | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | AT MOLLA PH2 ID 304252910 |  |  | BILL/01468/2023-2024 | 359/WBSEDCL-JJM | 20/02/2024 | 20/02/2024 | WBSEDCL | 5.41 | 0 | 0 | 0
7 | MURSHIDABAD | Kandi | Berhampore Mechanical | MOLLA PIPED WATER SUPPLY SCHEME | SM/14947 | New | AT MOLLA PH 1 ID 304252903 |  |  | BILL/01466/2023-2024 | 358/WBSEDCL-JJM | 20/02/2024 | 20/02/2024 | WBSEDCL | 3.88 | 0 | 0 | 0
Total | [13 empty] | 499.7 | 35.27 | 7.06