## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti-II | Berhampore Mechanical | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under MAHENDRAPUR ground water based water supply scheme under Block_ Suti-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000692/2023-2024 | 3811/MEDB | 03/11/2023 | 03/02/2024 | B. T. PROJECTS PVT. LTD. | 34.2 | 0 | 0 | 0
2 | MURSHIDABAD | Suti-II | Murshidabad Division | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | Material Requisition To Resource Division |  |  | RTOR000291/2023-2024 | 1230/MURD/33 | 04/05/2023 | 04/05/2023 | Resource Division | 27.6 | 0 | 0 | 0
3 | MURSHIDABAD | Suti-II | Berhampore Mechanical | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | NEW CONNECTION AT MAHENDARPUR PH-I |  |  | BILL/00631/2024-2025 | 187/WBSEDCL-JJM | 09/08/2024 | 09/08/2024 | WBSEDCL | 3.83 | 0 | 0 | 0
4 | MURSHIDABAD | Suti-II | Berhampore Mechanical | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | NEW CONNECTION AT MAHENDRAPUR PH-II |  |  | BILL/01246/2024-2025 |  | 13/12/2024 | 13/12/2024 | WBSEDCL | 5.13 | 0 | 0 | 0
5 | MURSHIDABAD | Suti-II | Berhampore Mechanical | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | NEW CONNECTION AT MAHENDARPUR PH-1 |  |  | BILL/00618/2024-2025 |  | 02/08/2024 | 02/08/2024 | WBSEDCL | 3.83 | 0 | 0 | 0
6 | MURSHIDABAD | Suti-II | Murshidabad Division | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | Installation of dual power based(Solar & electric) stand alone community purification plant(CWPP) FOR BALANCE 18 UNCOVERED habitations WHERE ARSENIC CONCENTRATION IS .01 TO .015 in the left out Arsenic affected habitations in the different block under Murshidabad Division P.H.E. Dte. at Murshidabad District. HABITATION-MAHENDRAPUR(4UNITS), VILLAGE-MAHENDRAPUR, BLOCK-SUTI-II | ASSISTANT ENGINEER | Junior Engineer 3,JUNIOR ENGINEER 6 | ORD/001629/2021-2022 | 459/MURD | 21/02/2022 | 07/04/2022 | ULTRA CONSTRUCTION. | 51.83 | 0 | 0 | 10
7 | MURSHIDABAD | Suti-II | Murshidabad Division | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | Formal work order for MAHENDRAPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jivan Mission of Suti-II Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000857/2022-2023 | 802/MURD | 22/03/2023 | 01/01/2026 | C.X. CONSTRUCTION & CO | 359.8 | 24.99 | 6.94 | 30
8 | MURSHIDABAD | Suti-II | Murshidabad Division | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 5.18 | 2.05 | 100
Total | [13 empty] | 739.48 | 30.17 | 4.08