## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti - II | Murshidabad Division | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | Material Requisition To Resource Division |  |  | RTOR000291/2023-2024 | 1230/MURD/33 | 04/05/2023 |  | Resource Division | 27.6 | 0 | 0 | 0
2 | MURSHIDABAD | Suti - II | Berhampore Mechanical | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under MAHENDRAPUR ground water based water supply scheme under Block_ Suti-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000692/2023-2024 | 3811/MEDB | 03/11/2023 | 01/02/2024 | B. T. PROJECTS PVT. LTD. | 34.2 | 0 | 0 | 0
3 | MURSHIDABAD | Suti - II | Murshidabad Division | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 0 | 0 | 100
4 | MURSHIDABAD | Suti - II | Murshidabad Division | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | Formal work order for MAHENDRAPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jivan Mission of Suti-II Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000857/2022-2023 | 802/MURD | 22/03/2023 | 21/03/2024 | C.X. CONSTRUCTION & CO | 359.8 | 0 | 0 | 0
5 | MURSHIDABAD | Suti - II | Murshidabad Division | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MAHENDRAPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti- II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000617/2023-2024 | 3389/MURD | 01/11/2023 | 22/11/2023 | TAPAN DAS | 18.56 | 4.17 | 22.49 | 50
6 | MURSHIDABAD | Suti - II | Berhampore Mechanical | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | NEW CONNECTION AT MAHENDARPUR PH-1 |  |  | BILL/00618/2024-2025 | null | 02/08/2024 |  | WBSEDCL | 3.83 | 0 | 0 | 0
7 | MURSHIDABAD | Suti - II | Berhampore Mechanical | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. | SM/15047 | New | NEW CONNECTION AT MAHENDARPUR PH-I |  |  | BILL/00631/2024-2025 | null | 06/08/2024 |  | WBSEDCL | 3.83 | 0 | 0 | null
Total | [13 empty] | 701.08 | 4.17 | 0.6