## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Samserganj | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/15051 | New | Material Requisition To Resource Division |  |  | RTOR000268/2023-2024 | 1230/MURD/11 | 04/05/2023 | 04/05/2023 | Resource Division | 22.61 | 0 | 0 | 0
2 | MURSHIDABAD | Samserganj | Berhampore Mechanical | NAPARA PIPED WATER SUPPLY SCHEME. | SM/15051 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under NAPARA ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000696/2023-2024 | 3808/MEDB | 03/11/2023 | 03/02/2024 | ORIENTAL ENGINEERING CO. | 20.86 | 12.05 | 57.78 | 10
3 | MURSHIDABAD | Samserganj | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/15051 | New | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NAPARA Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 6 | ORD/000621/2023-2024 | 3408/MURD | 02/11/2023 | 23/11/2023 | TAPAN DAS | 9.28 | 7.95 | 85.69 | 100
4 | MURSHIDABAD | Samserganj | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/15051 | New | Material Requisition To Resource Division |  |  | RTOR000383/2023-2024 | 495/MURD/14 | 15/02/2024 | 15/02/2024 | Resource Division | 5.03 | 0 | 0 | 0
5 | MURSHIDABAD | Samserganj | Berhampore Mechanical | NAPARA PIPED WATER SUPPLY SCHEME. | SM/15051 | New | NEW CONNECTION AT NAPARA PH-II |  |  | BILL/00221/2024-2025 | 60/WBSEDCL-JJM | 06/05/2024 | 06/05/2024 | WBSEDCL | 11.52 | 0 | 0 | 0
6 | MURSHIDABAD | Samserganj | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/15051 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sagarpara Part-A, Kohetpur and Napara Water Supply Scheme under Islampur & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER |  | ORD/000668/2022-2023 | 3409/MURD | 22/12/2022 | 05/02/2023 | R.K. DRILLING SERVICES | 23.56 | 0 | 0 | 0
7 | MURSHIDABAD | Samserganj | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/15051 | New | Formal work order for the work of NAPARA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Samserganj Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | ASSISTANT ENGINEER,JUNIOR ENGINEER 2 | ORD/000735/2022-2023 | 376/MURD | 10/02/2023 | 31/07/2025 | MANDAL CONSTRUCTION AND CO. | 241.91 | 122.24 | 50.53 | 45
8 | MURSHIDABAD | Samserganj | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/15051 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 4.75 | 1.87 | 100
9 | MURSHIDABAD | Samserganj | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. | SM/15051 | New | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well, 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KADOA Zone -II & NAPARA Water Supply Scheme at Head Work Site under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,Junior Engineer 3 | ORD/000015/2024-2025 | 1754/MURD | 13/06/2024 | 21/08/2025 | R.K. DRILLING SERVICES | 11.79 | 0 | 0 | 100
Total | [13 empty] | 599.82 | 146.99 | 24.51